CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	1

# DEVELOPMENT OF CONSTRUCTION MANAGEMENT FRAMEWORK FOR SHORELINE PROTECTION STRUCTURES BASED ON COASTAL EROSION RISK LEVELS IN APARRI, CAGAYAN

Presented to the faculty of College of Engineering and Architecture

## CAGAYAN STATE UNIVERSITY

Carig, Campus Tuguegarao City, Cagayan

In Partial Fulfillment

of the Requirements for the Degree

## BACHELOR OF SCIENCE IN CIVIL ENGINEERING

RIZABELL F. BRUNO SANDARA MARIE M. CABAUATAN

ROSS ANN D. MORA PHOEBE KATE S. UBANDO

April 2026

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	2

## APPROVAL SHEET

# This thesis titled “DEVELOPMENT OF CONSTRUCTION MANAGEMENT FRAMEWORK FOR SHORELINE PROTECTION STRUCTURES BASED ON COASTAL EROSION RISK LEVELS IN

APARRI CAGAYAN”, prepared and submitted by RIZABELL F. BRUNO, SANDARA MARIE M. CABAUATAN, ROSS ANN D. MORA, and PHOEBE KATE

S. UBANDO in partial fulfilment of the requirements for the degree, Bachelor of Science in Civil Engineering major in Construction Engineering Management, is hereby recommended for proposal defense.

## ENGR. MARK LESTER CAGURANGAN

Adviser

Approved by the Tribunal on Oral Examination with a grade of 	.

## ENGR. JOWELL JOHN B. TALOSIG

Chairman

ENGR. ARISTOTLE JAMES M. AGANON   ENGR. FELIPE NEIL C. PINTUCAN

Member	Member

## ENGR. JOSEPH R. CABALBAG, ME

Department Chair

Accepted and approved partial fulfillment of the requirements for the degree, Bachelor of Science in Civil Engineering major in Construction Engineering Management.

April 29, 2026	ENGR. JOHN MICHAEL B. CASIBANG, MSc

Date	Dean, College

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	3

## TABLE OF CONTENTS

APPROVAL SHEET	2

TABLE OF CONTENTS	3

PROPOSAL SUMMARY	5

CHAPTER I	1

THE PROBLEM AND ITS BACKGROUND	1

  - Introduction	1

  - Statement of the Problem	3

  - Objective of the Study	4

  - Conceptual Framework of the Study	4

  - Hypothesis/Assumption of the Study	5

  - Significance of the Study	5

  - Scope and Delimitation	6

  - Definition of Terms	7

CHAPTER II	9

REVIEW OF RELATED LITERATURE	9

  - Coastal Erosion Assessment	9

  - Remote Sensing, GIS and Erosion Analysis	13

  - Erosion Classification	15

  - Risk Classification	19

  - Coastal Risk Mapping	21

  - Prioritization of Coastal Management Areas	22

  - Coastal Protection and Management Strategies	23

    - Hard Engineering Approaches	24

    - Soft Engineering Approaches	25

    - Hybrid Coastal Protection Approaches	25

    - Selection of Appropriate Coastal Protection Measures	26

  - Instrument Validation and Reliability Assessment	26

  - Dynamic Shoreline Vulnerabilities and Structural Performance in the Philippines... 29

  - Synthesis	30

CHAPTER III	33

METHODOLOGY	33

  - General Overview	33

  - Study Area	34

  - Research Design	35

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	4

  - Population and Sample	36

  - Research Instrument	36

  - Data Gathering Procedure	37

  - Risk Assessment Method	39

  - Evaluation and Ranking of Shoreline Protection Structures	42

  - Framework Development Process	44

  - Reliability Test	46

  - Statistical Tools and Treatment	47

  - Ethical Consideration	51

CHAPTER IV	52

RESULTS AND DISCUSSION	52

  - Introduction	52

  - Profile of the Expert Respondents	52

  - Evaluation of Shoreline Protection Structures	56

CHAPTER V	58

CONCLUSION AND RECOMMENDATION	58

  - Summary	58

  - Conclusion	58

  - Recommendations	59

REFERENCES	60

APPENDICES	61

Appendix A. Guide to Appendices	61

Appendix B. Typical Appendix Contents	62

REFERENCES	63

APPENDICES	73

Appendix A. Work Breakdown Schedule	73

Appendix B. Sample Research Questionnaire	74

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	5

## PROPOSAL SUMMARY

TITLE	:	DEVELOPMENT OF CONSTRUCTION MANAGEMENT FRAMEWORK FOR SHORELINE PROTECTION STRUCTURES BASED ON COASTAL EROSION RISK LEVELS IN APARRI, CAGAYAN

RESEARCHER/S :	RIZABELL F. BRUNO

SANDARA MARIE M. CABAUATAN ROSS ANN D. MORA

PHOEBE KATE S. UBANDO

INSTITUTION	:	CAGAYAN STATE UNIVERSITY CARIG CAMPUS DEGREE	:	BACHELOR OF SCIENCE IN CIVIL ENGINEERING YEAR	:	2026

ADVISER	:	ENGR. MARK LESTER CAGURANGAN

This study will address the increasing coastal erosion in Aparri, Cagayan, which will continue to threaten coastal communities, infrastructure, and natural resources due to both natural processes and human activities. Although efforts have been made in building shoreline protection structures like seawalls, revetments, and mangrove rehabilitation, there is still a need to provide an organized and risk-oriented framework that will dictate the choice and management of such structures. This will ensure proper decision making regarding shoreline protection methods.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	6

The study will develop a framework based on coastal erosion risk levels derived from shoreline change analysis, while coastal erosion factors are assessed to support and explain shoreline behavior. It will categorize shorelines according to risk levels (low, medium, and high), conduct an analysis and comparison of viable shoreline protection structures through expert judgement, and prioritize such structures based on their viability and effectiveness.

The study will use a mixed method research design wherein qualitative techniques will be employed to determine factors based on field observations and secondary information while quantitative techniques will be used in classifying risks and evaluating shoreline protection structures using Likert Scale questionnaire and weighted mean techniques. Geographic Information System (GIS) will likewise be used to assess shoreline changes and develop erosion risk maps. The combination of qualitative and quantitative research methodologies will ensure that the framework developed is comprehensive, reliable, and grounded in both technical analysis and expert validation.

The results of the study will form the basis for effective selection of the appropriate shoreline protection structures through the use of a structured and data-oriented approach. The suggested model can be used as an effective tool by engineers and planners in their efforts to improve coastal management practices. In addition, the research work will lead to the development of more effective and sustainable approaches to shoreline protection in Aparri, Cagayan. At the same time, the model will model ensure improved decision making by focussing on interventions based on real conditions at the sites instead of generic solutions. Another contribution of the study lies in long term

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	7

planning for future shoreline protection, including both effectiveness and feasibility of construction management. Moreover, the research will help to develop more proactive attitudes toward the problem, moving beyond the response stage into prevention.

Keywords: coastal erosion;shoreline protection structures;risk assessment; likert scale; GIS analysis

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	1

## CHAPTER I

## THE PROBLEM AND ITS BACKGROUND

### Introduction

Coastal erosion can be viewed as a major problem that has been concerned to the environmental and engineering fields, considering the permanent loss of land, infrastructures, and natural environments such as mangroves and beaches that act as natural storm protectors. Scientific studies have shown that 70% of the world's sandy beaches experience erosion, which has become a threat to the world’s coastal ecosystems and the highly populated communities (WS Dong et al., 2024). Despite the fact that more than 30% of the world’s coastline is occupied by beaches, which is a major threat of disappearance due to rising sea levels, storm surges, and human induced environmental changes. In addition to that, Rocha et al., 2023 affirms that this problem has come to be of great concern, leading to the loss of land due to erosion in coastline, which affects millions of people who rely on the coastal environment to survive.

In the case of the Philippines, coastal erosion has been a problem given the length of the coastline and the severe weather conditions. The country has been known to be one of the most disaster-prone countries in the world, with an average of 20 tropical cyclones every year (Rivera and Dela Vega et al., 2025). Apart from typhoons, another cause of coastal erosion in the country is the existence of monsoon winds. The southeast and northeast monsoons lead to prolonged rough seas, which cause erosion through strong winds that gradually weaken the coastline (Taslin et al., 2024).

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	2

As pointed out in Nguyen et al., (2025), natural events only turn into disaster when they begin to negatively affect people’s lives, economic activities, and production systems. It is not possible to avoid natural hazards, but it is possible to minimize the negative impacts of these phenomena through proper planning and application of effective disaster risk reduction and adaptation. It is, therefore, necessary to enhance the resilience of the coastal areas, particularly those with high population and economic zones. The issue of climate change has already started affecting the Philippines through the rise in sea levels and the intensification of the levels of monsoon waves and currents. The issue of coastal erosion is, therefore, expected to worsen in the Philippines.

At the local scale, the situation in Aparri, Cagayan, is a clear indication of the worsening problem of coastal erosion in Northern Luzon. Aparri has a total land area of 28,664 ha and 18 km coastline (Ballad et al., 2021). In relation to this, erosion along the coastline of Aparri, Cagayan is influenced by intense national processes and human activities. The Local Government Unit (LGU) of Aparri, along with other national government agencies, worked to reduce coastal erosion by implementing shoreline protection projects including seawalls, revetment, and mangrove rehabilitations (DPWH et al., 2021). However, it is observed that most of these projects were implemented as a response measure to the problem after the erosion has already caused damage to the shoreline and its surrounding areas. The evaluation of the effectiveness of these projects is essential to determine whether these projects have successfully reduced the rates of erosion and increased the stability of the shoreline (DB Angnuureng et al 2025). Even though various approaches and frameworks manage coastal zones, existing frameworks

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	3

have limitations, such as being overly technical and lacking consistent application across different regions which reduces their effectiveness in addressing coastal erosion conditions (Toledo et al., 2025).

### Statement of the Problem

The coastal regions of Aparri, Cagayan are currently becoming more susceptible to erosion because of the influence of natural phenomena such as waves, tidal currents, and sedimentation along with human-made factors like coastal development and changing land use. While many different shoreline structures exist for the purpose of erosion control, their application and implementation are usually not determined based on an evaluation of the erosion-related hazards and the degree of risks, which results in inefficient approaches and inappropriate choices of shore protection systems in certain localities.

Despite the numerous approaches and frameworks used to handle coastal areas, existing frameworks have limitations such as over technicality and inconsistency across regions making them inefficient when dealing with coastal erosion problems.

In response, this research will seek to categorize their erosion risks based on low, medium, and high risks. Assess and compare the best types of shoreline protection structures according to expert opinion and weighted means. At the end of the day, the research will attempt to establish a well-established construction management framework that is appropriate for different erosion risks.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	4

### Objective of the Study

    - General Objective

The development of a construction management framework for shoreline protection structures in Aparri, Cagayan based on coastal erosion risk levels.

### Specific Objectives

      - To classify various levels of coastal erosion risk into low, medium, and high-risk levels.

      - To determine the most suitable shoreline protection structures in terms of their perceived efficiency and feasibility.

      - To rank the most suitable shoreline protection structures depending on the various coastal erosion risk levels.

      - To develop a construction management framework for shoreline protection structures depending on the coastal erosion risk levels in Aparri, Cagayan.

### Conceptual Framework of the Study

The study determines erosion risk levels using shoreline change rates derived from GIS analysis. Coastal erosion factors are assessed to explain shoreline behavior. These outputs are used to guide the selection of appropriate shoreline protection structures and to develop a construction management framework.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	5

### Hypothesis/Assumption of the Study

With the problem raised on this study, the following hypothesis will be tested:

- Ho1: Coastal Erosion Risk Levels have no significant difference on the perceived efficiency and feasibility of shoreline protection structures in Aparri, Cagayan.

- Ha1: Coastal Erosion Risk Levels have a significant difference on the perceived efficiency and feasibility of shoreline protection structures in Aparri, Cagayan.

### Significance of the Study

This study will benefit various stakeholders because it proposes the creation of a construction management framework in the context of coastal erosion factors in Aparri.

For local government units (LGUs) and policymakers, this will become a useful framework in their efforts to manage the coastlines and make plans accordingly in terms of priority allocation of budget to different locations that have higher erosion risk levels than others

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	6

For the coastal communities of Aparri, Cagayan, this study will contribute to developing more effective ways to address the problem of coastal erosion to minimize the risks associated with it and safeguard the lives, properties, and livelihoods of people in the community.

For civil engineers and construction practitioners, who are provided in the research with the risk-based construction management framework supported by coastal erosion factors that may serve as an instrument of their work related to shoreline protection.

For students and teachers, especially those pursuing civil engineering studies are also potential beneficiaries, as the research will be considered by them as a reference concerning coastal erosion analysis, risk classification and construction management.

For future researchers, this research offers insights for developing a framework for assessing coastal erosion, classifying risks, and management of construction. The approach and results presented in this study can also be adopted or improved to be used in different coastal areas that experience similar issues with coastal erosion.

### Scope and Delimitation

This research deals with the construction management framework of the shoreline protection structures at the shoreline areas of Aparri, Cagayan considering the risk classifications. The study will consider the entire shoreline areas of Aparri, Cagayan particularly those of the coastal barangays namely, Linao, Maura, Punta, San Antonio, Bulala Sur, Bulala Norte, Dodan, and Paddaya, which make up a common shoreline experiencing coastal erosion.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	7

As part of the study, the coastal erosion risk levels will also be classified as low, medium, and high depending on the observed conditions. The efficiency and feasibility of the existing shoreline protection structures will be evaluated, compared, and ranked based on expert judgment and weighted means analysis. Based on these data, the construction management framework of the shoreline protection structures will be developed to provide guidelines on coastal protection based on different risk levels of coastal erosion.

The study will consider the selected continuous shoreline of Aparri, Cagayan, specifically covering the coastal barangays of Linao, Maura, Punta, San Antonio, Bulala Sur, Bulala Norte, Dodan, and Paddaya. The study does not cover any other coastal areas outside this continuous shoreline. Also, the study will be limited to the existing shorelines protection system and no new structure will be designed or implemented in this study. Moreover, the study will be based on the existing data, field survey, and expert opinions during the research period and will not involve physical modeling of coastal processes.

### Definition of Terms

Anthropogenic. Shoreline change caused by human activities.

Coastal Erosion Factors.These factors act as the design constraints of the framework

Construction Management Framework ( CMF). It provides a standardized protocol for engineers to ensure that the project delivery is scientifically sound, legally compliant, and specifically adapted to the Cagayan Environment.

Erosion Risk Map. A spatial representation generated using Geographic Information System (GIS) that illustrates the distribution of shoreline segments classified

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	8

into low, medium, and high erosion risk levels based on computed shoreliSelectin e rates. This map is used to identify priority areas for intervention and supports decision-making in selecting appropriate shoreline protection measures.

Geographical Information System (GIS). The foundational platform is used to map erosion hotspots and visualize future shoreline projections, allowing project managers to make data-driven decisions during the planning stage.

Hybrid Engineering. This is Mixed Defense. It means using both "hard" things like concrete walls and "soft" things like planting mangroves. It’s like having a shield (the wall) and a cushion (the plants) together.

Morphological Flux. This term defines the “instability” that the CMF must manage.

Scouring. It is the primary cause of structural failure in the region.

Shoreline. The line where the land meets the sea, used as a reference to track changes along the coast.

Shoreline Protection Structures. These are the physical assets managed by the framework.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING AND ARCHITECTURE	9

## CHAPTER II

## REVIEW OF RELATED LITERATURE

### Coastal Erosion Assessment

Coastal erosion is a dynamic geomorphological process involving the gradual removal of shoreline materials through the action of waves, tides, currents, storm surges, and sea-level rise. Human activities, such as coastal development, land reclamation, sand mining, and the construction of coastal infrastructure, further accelerate shoreline retreat by disrupting the natural sediment transport system. As climate change continues to intensify coastal hazards, shoreline erosion has become one of the most pressing environmental concerns worldwide because of its impacts on coastal ecosystems, infrastructure, and communities (Tsiakos, C. A. D., & Chalkias, C., 2023).

Recent studies emphasize that understanding coastal erosion requires continuous monitoring of shoreline movement over time. According to Tsiakos, C. A. D., & Chalkias,

C. (2023), shoreline retreat results from the combined effects of natural coastal processes and anthropogenic pressures. Their review explained that increasing sea levels, stronger storm events, and expanding coastal development have accelerated shoreline changes in many parts of the world, highlighting the need for accurate and timely monitoring to support sustainable coastal management. They further noted that advances in remote sensing technologies have significantly improved the ability of researchers to detect, monitor, and quantify shoreline changes across various coastal environments.

Similarly, Cavalli, R. M. (2024) conducted a systematic review of remote sensing applications in coastal environments and found that coastal zones are highly vulnerable

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	10

because they are continuously influenced by interactions among terrestrial, marine, atmospheric, and human-induced processes. The review demonstrated that remote sensing has become an essential tool for monitoring coastal phenomena due to its ability to provide consistent spatial and temporal observations over large geographic areas. The author also emphasized that regular monitoring of shoreline conditions enables early identification of erosion-prone areas, allowing government agencies and coastal managers to implement evidence-based mitigation and adaptation strategies.

The growing importance of shoreline monitoring is likewise supported by Sun, W. et al. (2023), who explained that coastlines represent one of the most dynamic boundaries on Earth because they constantly respond to natural processes and human activities. Their review highlighted that accurate coastline extraction is fundamental for assessing shoreline evolution, evaluating erosion and accretion patterns, and supporting coastal planning and hazard mitigation. The authors further noted that recent developments in satellite remote sensing have greatly improved the precision and efficiency of shoreline mapping, enabling researchers to perform long-term analyses of coastal change.

Furthermore, the need to develop a local management framework becomes more critical because of the “triple whammy” hitting Aparri, which includes rising sea levels, heavier monsoon seasons, and the distinctive sediment processes at the mouth of the Cagayan River. Civil engineering deals with the designs for constructing seawalls and revetments, while construction management takes care of making them last.

Among the most geographically vulnerable areas in the Philippines is the Municipality of Aparri in the province of Cagayan, which is situated at the delta of

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	11

Cagayan River, considered to be the longest river system in the entire country, and is also exposed to the strong energy currents of the Babuyan Channel. This area has been experiencing a constant battle between the discharge of water from the river and the energy currents coming from the sea, wherein in recent years the latter has prevailed by causing substantial loss of land.

Coastal erosion can be caused by natural factors as well as anthropogenic factors. According to Felipe, A. J. et al. (2026), the erosion processes with the lower Cagayan River are caused by the presence of very high levels of sand and silt (above 95%). Additionally, International Tests conducted by Woodroffe, et al. (2025) reveal that “sediment starvation”, which usually results from upstream practices like mining and building dams, is the main reason for coastal erosion. When there is not enough sand being brought by the river to the river mouth in Aparri, there will be an intrusion by the sea because the seawalls constructed have not taken this scenario into consideration.

An important and frequently underestimated phenomenon behind erosion is the relative sea level rise (RSLR) coupled with land subsidence. According to OECD (2026) and Nature Communications (2022), while global sea levels rise, some coasts in the Philippines are actually subsiding because of excessive use of groundwater resources and sediment compaction in river deltas. In estuaries such as Aparri, this “doubled effect” creates deeper water near the shore where high-energy waves may occur without being weakened by the seafloor. As a result, such a situation increases the pace at which coastal infrastructure is undermined. According to Nerves, A. et al. (2024), the most vulnerable areas to change are those located along the coast at river deltas (such as Aparri). As was

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	12

demonstrated through GIS maps, changes within the shoreline along such river delta outlets can exceed up to 150+ meters during a span of 30 years.

Based on data from Calapini, W. D. et al. (2025), the rate of sea-level rise for the West Philippine Sea and Northern Luzon is measured to be 4-6 mm/yr, more than double the global rate. Coupled with land subsidence, seawalls, which are typically built at a certain height, can easily fail through overtopping. In high energy areas such as Aparri, vertical structures tend to promote erosion by reflecting waves, thereby creating scour holes at the bottom of the structures. This problem can be addressed through an approach based on a preference for slopping/staged revetment designs.

In addition, an interference caused by man in terms of sediment movement has an important effect on the “starvation” of Aparri coastline. As revealed by research published in Elsevier’s Anthropocene (2023), the presence of large infrastructures and mining operations at the upper parts of the Cagayan River Basin has drastically altered the amount of sand carried to the river mouth. Whenever this natural movement of sedimentation is prevented, then the “longshore drift”will cause erosion by carrying away more sediments than it deposits. This is why contemporary construction models need to incorporate Sediment Impact Assessments (SIA), which will determine whether the shoreline structure will hasten erosion in other barangays.

The effect of extreme weather frequency plays an important role in the durability of the defenses located within northern Cagayan. As per the findings from Nieuwenhout,

C. et al. (2023), due to the clustering of typhoons, meaning several typhoons occurring successively, there would be no time for the beach to recover from its initial state post

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	13

occurrence of only one storm. Such a process leads to weathering of concrete and dislodging of armor blocks of revetments.

The literature consistently demonstrates that coastal erosion is not only an environmental issue but also a significant socio-economic concern. Continuous shoreline monitoring provides scientific evidence necessary for coastal resource management, infrastructure protection, disaster risk reduction, and sustainable land-use planning. These findings support the present study which aims to assess shoreline changes and erosion rates using geospatial techniques to identify erosion-prone coastal areas and provide information that can assist local planning and coastal management decisions.

### Remote Sensing, GIS and Erosion Analysis

Remote sensing and Geographic Information Systems (GIS) have become essential technologies for monitoring shoreline dynamics because they provide efficient, accurate, and cost-effective means of analyzing coastal changes over large spatial and temporal scales. Compared with conventional field surveys, satellite remote sensing enables repeated observations of coastal environments, while GIS facilitates the storage, processing, visualization, and analysis of spatial data. The integration of these technologies allows researchers to identify shoreline positions from multi-temporal satellite imagery, quantify shoreline movement, and evaluate erosion and accretion patterns with greater precision. These capabilities have made remote sensing and GIS indispensable tools in coastal management, environmental monitoring, and disaster risk reduction (Tsiakos, C. A. D., & Chalkias, C. 2023).

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	14

The authors explained that recent advances in remote sensing have significantly improved shoreline monitoring through the availability of high-resolution satellite imagery, machine learning algorithms, and GIS-based analytical techniques. The authors further stated that integrating remote sensing with GIS provides reliable spatial information for detecting shoreline retreat, assessing coastal erosion, and supporting evidence-based coastal planning and management.

Similarly, Cavalli, R. M. (2024) conducted a systematic review of remote sensing applications for coastal monitoring and found that satellite-derived data have become increasingly valuable for mapping coastal phenomena, including shoreline changes, coastal morphology, sediment dynamics, and environmental hazards. The review highlighted that remote sensing platforms provide continuous observations over extensive coastal regions, enabling researchers to monitor changes that would otherwise require significant time and financial resources through ground surveys. Furthermore, the study emphasized that integrating remotely sensed data with GIS enhances spatial analysis, allowing decision-makers to identify vulnerable coastal areas and develop appropriate mitigation strategies.

Supporting these findings, Sun, W. et al. (2023) reviewed recent developments in coastline extraction using remote sensing and reported that advances in Earth observation technologies have substantially improved the accuracy and efficiency of shoreline mapping. According to the authors, multi-temporal satellite imagery combined with GIS-based processing techniques enables researchers to monitor coastline evolution, quantify shoreline displacement, and evaluate coastal changes over extended periods.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	15

They also emphasized that remote sensing-derived shorelines provide essential baseline information for coastal management, hazard assessment, and sustainable development planning.

Likewise, Zhou, X. et al. (2023) noted that coastlines extraction has become one of the most fundamental applications of remote sensing because coastline represents the interface between terrestrial and marine environments. Their review discussed numerous shoreline extraction approaches using optical satellite imagery and GIS techniques, concluding that advances in image processing and spatial analysis have significantly improved the reliability of coastline delineation. The authors further explained accurate shoreline extraction is critical for monitoring coastal evolution, assessing erosion hazards, and supporting coastal resource management.

The reviewed literature consistently demonstrates that remote sensing and GIS provide reliable, efficient, and scientifically accepted methods for shoreline monitoring and coastal erosion assessment. Their capability to analyze historical and contemporary shoreline positions using multi-temporal satellite imagery supports accurate measurement of shoreline changes and erosion rates. These findings provide a strong theoretical foundation for the present study, which employs GIS and remote sensing techniques to extract shoreline positions and analyze coastal erosion trends within the study area.

### Erosion Classification

In contemporary coastal engineering literature, the shoreline is no longer conceptualized as a static, linear boundary, but rather as a highly dynamic, time-dependent socio-ecological interface where intense geomorphological exchanges occur between

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	16

terrestrial and marine systems (Li, C., & Fang, S., 2026). Consequently, shoreline change is defined as the net spatial and temporal horizontal displacement of this boundary line, manifesting as a bidirectional process: landward retreat (erosion) or seaward advancement (accretion) (Gao, W. et al., 202).

Recent studies emphasize that modern shoreline change trends are governed by a complex compounding relationship between natural hydrodynamic forces and accelerating human interventions (Tora, Dkawlama, et al., 2026).

- Natural Drivers: Chronic sea-level rise, fluctuating wave energy distributions, tidal currents, and episodic severe weather events (such as typhoons and storm surges) cause rapid short-term morphological flux (Tikekar, Omkar, et al., 2026).

- Anthropogenic Drivers: Human activities- such as coastal urbanization, land reclamation, sand mining, and the construction of maritime structures like ports, jetties-distrupt natural longshore sediment transport (Elemin, S. A. et al., 2026). This disruption traps sediment on the updrift side while causing severe sediment starvation and accelerated erosion along downdrift coastal cells.

To establish a quantifiable matrix for coastal risk levels, the End Point Rate (EPR) method serves as a primary metric for determining the net annualized rate for shoreline change between two distinct historical positions. As utilized in this study, the mathematical formulation is expressed as:

(𝑆 −𝑆 )

𝑇

Erosion Rate =   2	1

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	17

Where S2 represents the spatial shoreline position in the later year, S1 denotes the initial baseline position in the earlier year, and T signifies the time interval expressed in years. Within this algebraic structure, the sign of the numerical output indicates the directional behavior of the coast: negative computational product signifies landward retreat (erosion), whereas a positive product yields localized sediment accumulation (accretion). The standard engineering unit of measurement for this velocity vector is expressed uniformly in meters per year (m/year).

The mathematical rationale for employing a difference-over-time model is extensively validated in global spatial remote sensing studies. Research utilizing the Digital Shoreline Analysis System (DSAS) framework confirms that the linear EPR approach is highly reliable when evaluating long-term coastal changes where data points are constrained to specific historical map epochs or multi-decadal aerial surveys ( Thieler, et al., 2009). Because the formula requires only two operational shoreline vectors, it avoids the statistical over complication that can occur when intermediate historical maps contain missing or highly fragmented spatial data (USGS,2023).

Furthermore, applications within the Philippine marine architecture confirm the reliability of this formula in analyzing highly active river deltas and estuarine environments. A geographic study conducted by Nerves et al. (2024) tracking deltaic changes in open bay regions demonstrated that dividing cross-shore movement (ΔS) by chronological duration (T) provides a mathematically rigorous, repeatable baseline for capturing structural risk trends. Their findings confirmed that calculating the delta of orthogonal shoreline distances over explicit time intervals accurately captures severe,

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	18

localized erosion patterns driven by compounding monsoonal wave actions and deltaic sediment fluctuations.

The classification of shoreline erosion into different risk levels is an essential component of coastal hazard assessment because it enables researchers and decision-makers to identify areas requiring varying levels of intervention. Erosion rate thresholds provide a standardized basis for interpreting shoreline retreat and prioritizing coastal management strategies. Although, threshold values differ depending on coastal characteristics and study objectives, several studies have established that increasing shoreline retreat rates correspond to increasing erosion susceptibility.

The United States Geological Survey (USGS, 2023) recognizes shoreline retreat rate as one of the primary indicators of coastal vulnerability. According to the agency, sustained shoreline retreat of several meters per year reflects active coastal erosion, while higher retreat rates indicate severe coastal instability that may threaten infrastructures, ecosystems, and coastal communities. The USGS recommends that shoreline change rates must be incorporated into coastal hazard mapping to identify areas requiring management and protection measures. This reinforces the use of erosion rate thresholds as a basis for classifying shoreline erosion risk.

A global assessment conducted by Luijendijk et al. (2018) analyzed approximately 33 years of satellite-derived shoreline data covering more than 100,000 km. of sandy coastlines worldwide. This study found that coastlines experiencing shoreline retreat greater than 5 m/year represent rapidly eroding environments, while lower retreat rates generally indicate relatively stable shoreline conditions. The researchers emphasized that

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	19

areas with rapid erosion require priority attention because of their greater exposure to coastal hazards and land loss. These findings provide scientific support for using greater than 5 m/year as the threshold for high erosion risk.

Collectively, these studies demonstrate that shoreline erosion rates provide a scientifically sound basis for classifying erosion susceptibility and supporting coastal management decisions. Guided by these findings, an existing study by Osondu, I. et al. (2025) also adopts an erosion-risk classification of Low (<2 m/year), Medium (2-5 m/year), and High (>5 m/year). The authors explained that these thresholds were adopted from established coastal risk assessment frameworks to distinguish shoreline segments according to erosion severity. Coastlines experiencing erosion greater than 5 m/year were identified as highly vulnerable because they exhibited rapid shoreline retreat associated with strong hydrodynamic processes, while erosion rates below 2 m/year represented relatively stable shoreline conditions. Moderate erosion rates of 2-5 m/year indicated shoreline sections undergoing noticeable retreat that require continuous monitoring and appropriate coastal management measures.

### Risk Classification

In the architectural design of resilient coastal defense systems, the Erosion Rate serves as an objective, empirical measure of physical hazard intensity. It captures the long-term, backshore horizontal retreat of a boundary line under unconstrained conditions, typically computed via change models like the End Point Rate (EPR).

However, a high erosion rate does not automatically equate to a high Erosion Risk. As established by comprehensive natural disaster risk frameworks, Erosion Risk is a

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	20

multi-dimensional function that represents the potential for real asset loss, environmental degradation, or structural failure when a physical hazard intersects with human receptors, socioeconomic exposure, and structural vulnerability indicators (Ouyang & Wang, 2024).

For instance, a natural, unpopulated mangrove zone experiencing a rapid horizontal retreat of >5 m/yr exhibits a high erosion rate but presents a relatively low erosion risk due to its inherent ecological buffer and the absence of high-value structural assets. Conversely, a heavily built-up urban center or vital port facility situated along an estuary experiencing a lower retreat velocity of only 1 m/yr can represent an exceptionally high erosion risk because the local infrastructure has high exposure and susceptibility to immediate scouring, undermining, or structural collapse. Contemporary coastal management strategies emphasize that framework development must transition away from using raw physical baseline velocities alone, instead integrating complex exposure and vulnerability dimensions to prioritize structural implementations effectively (Ouyang & Wang, 2024). For instance, a natural, unpopulated mangrove zone experiencing a rapid horizontal retreat of >5 m/yr exhibits a high erosion rate but presents a relatively low erosion risk due to its inherent ecological buffer and the absence of high-value structural assets. Conversely, a heavily built-up urban center or vital port facility situated along an estuary experiencing a lower retreat velocity of only 1 m/yr can represent an exceptionally high erosion risk because the local infrastructure has high exposure and susceptibility to immediate scouring, undermining, or structural collapse.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	21

Contemporary coastal management strategies emphasize that framework development must transition away from using raw physical baseline velocities alone, instead integrating complex exposure and vulnerability dimensions to prioritize structural implementations effectively (Ouyang & Wang, 2024).

### Coastal Risk Mapping

Coastal risk mapping has become an essential component of shoreline management because it transforms quantitative erosion information into spatially explicit products that facilitate decision-making. By integrating shoreline change data, erosion-rate classifications, geographic information systems (GIS), coastal risk maps enable planners to identify erosion hotspots and visualize the spatial distribution of areas requiring intervention. Compared with tabular results, risk maps provide a clearer representation of the severity and extent of coastal hazards, allowing decision-makers to prioritize monitoring and mitigation efforts more effectively (Tzepkenlis, A. et al., 2022).

Recent studies demonstrate the growing application of GIS in coastal risk mapping. The authors developed an integrated coastal monitoring system that combined remote sensing, GIS, and machine learning to monitor coastal hazards, including shoreline erosion. Their study emphasized that spatial monitoring systems improve the detection of erosion hotspots and support evidence-based coastal management by integrating multiple geospatial datasets into a unified decision-making support framework.

Similarly, Thirumurthy, S. et al. (2022) integrated GIS with multi-criteria analysis to produce coastal vulnerability maps that identified areas with varying levels of susceptibility to coastal hazards. Their findings demonstrated that GIS-based spatial

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	22

classification enables coastal managers to distinguish between low-, medium-, and high-risk zones, thereby improving planning and resource allocation.

Likewise, Igbokwe, J. I. et al. (2024) utilized GIS and the Analytic Hierarchy Process (AHP) to model and map coastal erosion vulnerability. The study concluded that thematic erosion-risk maps provide an effective basis for identifying critical shoreline sections and developing appropriate management strategies.

In the planning phase of coastal engineering, deciding which structural or non-structural intervention is most appropriate relies heavily on Multi-Criteria Decision Analysis (MCDA). As researchers globally seek to balance ecological impact, economic cost, and engineering efficiency, quantitative decision matrices have become standard.

The reviewed literature supports the present study because the classified erosion rates are likewise converted into GIS-based coastal risk maps. Presenting erosion-risk classes spatially enables the identification of erosion hotspots and provides a practical tool for coastal planning, monitoring, and decision-making.

### Prioritization of Coastal Management Areas

The identification of priority coastal management areas is a fundamental step in erosion-risk assessment because coastal resources available for mitigation are often limited. Rather than implementing interventions uniformly across an entire coastline, management efforts are commonly directed toward shoreline segments exhibiting the greatest erosion severity and potential impacts. Prioritization enables government agencies and coastal managers to allocate financial, technical, and environmental resources more

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	23

efficiently while maximizing the effectiveness of erosion mitigation programs (Cao, C. et al., 2022).

Recent literature emphasizes the importance of prioritizing erosion-prone areas through spatial decision-supported approaches. Cao, C. et al., 2022 investigated the evolution of coastal erosion vulnerability in the Pearl River Estuary and demonstrated that identifying highly vulnerable shoreline sections provides valuable information for planning adaptive coastal management measures. The authors highlighted that spatial prioritization enables decision-makers to focus interventions on shoreline segments experiencing the most significant erosion pressures.

Furthermore, Tzepkenlis, A. et al. (2022) emphasized that integrated coastal monitoring systems not only identify hazard-prone locations but also function as decision-support tools that assist policymakers in determining where management actions should be implemented first. The study demonstrated that spatial prioritization strengthens coastal resilience by enabling timely and targeted interventions.

The reviewed studies support the present research because, after classifying shoreline erosion risk, the identified high-risk coastal segments serve as the basis for determining priority management areas. This approach provides a scientific basis for recommending which shoreline sections require immediate attention and supports evidence-based coastal planning.

### Coastal Protection and Management Strategies

Coastal protection strategies are implemented to minimize shoreline erosion, reduce the impacts of coastal hazards, and enhance the resilience of coastal communities

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	24

and ecosystems. Recent literature classifies coastal protection measures into hard engineering, soft engineering (nature-based solutions), and hybrid approaches, emphasizing that no single strategy is universally applicable because coastal environments differ in geomorphology, hydrodynamic conditions, sediment characteristics, and land use. Consequently, the selection of an appropriate coastal protection measure should be based on site-specific conditions and the severity of shoreline erosion (Amos, D., & Akib, S., 2023).

### Hard Engineering Approaches

Hard engineering approaches involve the construction of permanent structures that protect coastlines by resisting wave forces and reducing shoreline retreat. Common examples include seawalls, revetments, groynes, detached breakwaters, and bulkheads. These structures are widely implemented in densely populated coastal areas where critical infrastructure, transportation networks, and residential communities require immediate protection from erosion and coastal flooding. Although hard engineering provides effective shoreline stabilization, it may interrupt natural sediment transport, increase erosion in adjacent coastal areas, and require substantial construction and maintenance costs. Therefore, recent studies recommend that structural interventions be implemented only after comprehensive coastal assessment and engineering evaluation (Amos, D., & Akib, S., 2023).

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	25

### Soft Engineering Approaches

Soft engineering approaches utilize natural processes and ecosystem restoration to reduce shoreline erosion while maintaining ecological integrity. These measures include beach nourishment, dune restoration, mangrove rehabilitation, saltmarsh restoration, seagrass conservation, and living shorelines. Unlike conventional structural defenses, soft engineering techniques enhance sediment retention, dissipate wave energy, improve biodiversity, and provide multiple ecosystem services. Jordan, P., & Fröhle, P. (2022) emphasized that coastal ecosystems function as effective nature-based solutions by providing shoreline stabilization while simultaneously conserving coastal habitats. Likewise, Perricone, V. et al. (2023) reported that mangroves, coral reefs, oyster reefs, salt marshes, seagrasses, and other coastal ecosystems significantly attenuate wave energy and contribute to long-term shoreline protection,making them sustainable alternatives or complements to conventional engineering structures.

### Hybrid Coastal Protection Approaches

Hybrid coastal protection combines conventional engineering structures with nature-based solutions to achieve both structural stability and ecological sustainability. Rather than relying solely on hard or soft engineering, hybrid systems integrate engineered defenses with natural coastal ecosystems to enhance shoreline resilience under changing climatic conditions. Singhvi, A. et al. (2022) described this concept as a continuum ranging from traditional “grey” infrastructure to fully “green” nature-based interventions, emphasizing that integrated approaches provide greater adaptability to sea-level rise and future coastal hazards. Similarly, Perricone, V. et al. (2023) concluded

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	26

that combining engineering design with natural coastal ecosystems improves coastal protection while preserving environmental functions and ecosystem services.

### Selection of Appropriate Coastal Protection Measures

The selection of an appropriate coastal protection strategy should consider erosion severity, shoreline morphology, hydrodynamic conditions, environmental sensitivity, socio-economic factors, and the importance of exposed coastal assets. Amos, D., & Akib, S., 2023 emphasized that coastal protection measures should be selected according to site-specific coastal behavior because different shoreline environments respond differently to engineering interventions. Accordingly, recent literature recommends adaptive coastal management that combines scientific risk assessment with appropriate engineering interventions to maximize both shoreline protection and environmental sustainability.

The reviewed literature supports the present study because the identified coastal erosion risk levels provide the scientific basis for recommending suitable coastal protection measures. By matching erosion severity with appropriate hard engineering, soft engineering, or hybrid approaches, the proposed framework facilitates evidence-based decision-making for sustainable coastal management.

### Instrument Validation and Reliability Assessment

According to Sauvé, P. et al. (2022), selecting appropriate Coastal Defence Measures (CDMs)-such as concrete seawalls, rock armour, or soft interventions-is inherently complex due to conflicting stakeholder interests and localized wave dynamics. Their study establishes that an expert-driven weighting phase integrated into a systematic

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	27

decision matrix effectively minimizes bias and translates qualitative engineering judgement into a prioritized ranking system. This provides rigorous theoretical validation for using expert questionnaires scored on numerical scales (e.g., Likert scales and weighted means) to calculate structural suitability in targeted coastal areas.

Decision matrices are widely used in engineering and infrastructure planning to evaluate and rank alternative solutions based on multiple criteria. They provide a systematic and transparent approach for comparing alternatives by assigning scores to predetermined evaluation criteria, enabling decision-makers to identify the most suitable option. The method is particularly useful when technical, economic, environmental, and operational factors must be considered simultaneously (Dodgson, J. S. et al., 2009).

Furthermore, global adaptation initiatives emphasize that mapping indicators of technology options into a standardized decision matrix ensures that the overall value scores directly reflect localized environmental pressures. When criteria weights are distributed systematically (where the cumulative sum of weights equals 1.0), the resulting total weighted scores provide a reliable, transparent ranking mechanism to select the most viable shoreline protection technology for vulnerable coastal zones (Wilson, E. Tenesee, and T. N. A. E. P. A. Liberia, 2019).

Developing a comprehensive construction management framework requires moving away from traditional, fragmented “design-and-forget” paradigms toward whole-life-cycle optimization. In marine construction, frameworks must reconcile policy constraints, socio-environmental factors, and local technical capacities.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	28

Gu, J. et al. (2025) introduced a comprehensive “conflict-coordination framework” for coastal defense lines, proving that managing structural implementation across its lifecycle requires an interdisciplinary framework combining baseline technical capacity with site-specific risk assessments. The study reveals that integrating ecological metrics with hard engineering parameters (such as seawall positioning and structural durability) within a unified management framework successfully coordinates multi-objective outcomes-reducing environmental conflict intensity while maximizing structural resilience.

Instrument reliability is an important aspect of questionnaire development because it determines the consistency of the items in measuring the intended construct. A reliable instrument produces stable and consistent results, thereby increasing the credibility of the data collected. Among the available measures of reliability, Cronbach's Alpha is the most widely used statistic for evaluating the internal consistency of multi-item questionnaires (Taber, K. S., 2018). It measures the extent to which questionnaire items are correlated and collectively assess the same concept.

Methodological literature generally considers a Cronbach's Alpha coefficient of

0.70 or higher as the minimum acceptable level of internal consistency, indicating that the questionnaire items reliably measure the intended construct (Taber, K. S., 2018). Therefore, the present study adopts Cronbach's Alpha to determine the reliability of the developed questionnaire before its administration to experts, ensuring that the instrument provides consistent and dependable measurements.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	29

### Dynamic Shoreline Vulnerabilities and Structural Performance in the Philippines

In the local context, the Department of Public Works and Highways (DPWH) sets baseline standard specifications for public infrastructure yet coastal structures in regions like Northern Luzon face unique field implementation vulnerabilities. This disconnect between conceptual design and actual construction workmanship often leads to premature failures during extreme weather events.

A post-disaster construction audit conducted by Narafu, T. et al. (2015) in the Philippines evaluated the performance of infrastructure under severe typhoon and surge forces, explicitly categorizing the main drivers of structural failure into poor quality of materials, deficit localized design, lack of post-construction maintenance, and poor workmanship during site execution. The study concluded that standard design guidelines alone are insufficient; there is a critical need for comprehensive capacity development and common structural management frameworks on-site to guide DPWH personnel and contractors throughout the actual construction phases.

Furthermore, engineering reliability assessments of Philippine coastal defenses emphasize that wave impact forces act significantly harsher on structural stability than standard terrestrial forces. Recent simulations of local mega-dikes show that resisting structural failures requires dynamic site management frameworks that account for localized wave elevations, embankment stability,and soil-sliding resistance, reinforcing the necessity of matching structural selection explicitly to coastal erosion risk levels (Bartolome, I. S., & Griño Jr, A., 2026).

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	30

### Framework Development Process

Developing an effective framework for shoreline protection requires integrating scientific risk assessment with engineering planning, construction management, and long-term monitoring. Recent studies emphasize that coastal infrastructure should follow a systematic framework that begins with hazard assessment, continues through planning and design, and extends to implementation and post-construction evaluation to ensure sustainability and resilience against coastal hazards.

### Synthesis

It is evident from the literature that coastal erosion is becoming an escalating geomatics and socioeconomic risk all around the world due to a series of interactions between nature-based hydrodynamics and human activities. In terms of methodology, the combination of Remote Sensing and Geographic Information Systems (GIS) with linear computing models like the End Point Rate (EPR) method has already been proven scientifically accurate for quantification of shoreline changes over decades and pinpointing areas with erosion risk. Moreover, the literature reveals the need for shifting risk assessment frameworks into multi-criteria analyses in order to consider not only physical speeds but also local vulnerabilities.

Despite these advancements, a critical examination of global and local literature reveals three major research gaps that remain unaddressed:

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	31

- Paradigm Gap Between Erosion Mapping and Structural Construction: Although there is a lot of information available on the geospatial analysis techniques used to map erosion rates and assess any natural or man-made structural protection measures, there is a clear gap between planning-level macro-analysis and actual construction implementation. All spatial analysis techniques are concerned with categorizing risks and making a passive map out of those, yet do not convert risk categorizations into a construction management paradigm that is required to withstand difficult estuary conditions.

- The Ineffectiveness and Inconsistency of Standard, Reactive Coastal Management Approaches: From a national perspective, prevailing coastal management practices have been known to have inherent weaknesses, typically identified as either too technical or lacking local environmental fine-tuning in various geomorphic environments. In locations such as Aparri, Cagayan, where there is a unique "triple whammy" effect of rapid sea level rise, intense monsoonal clustering, and extreme sediment starvation, design standards are always applied on a reactive basis after damage has been incurred. Literature suggests that in the absence of an alignment between physical risk level and engineering feasibility at the site level, standard structures are likely to fail due to overtopping, wave reflection scouring, and concrete weathering among others.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	32

- Shortcomings in Dynamic Structural Integrity Decision-Making for Field Application: Post-disaster audits in the Philippines indicate that traditional infrastructure design guidelines are not sufficient enough to cope with the highly dynamic marine environment since they do not include capacity building and life cycle management of sites to direct DPWH officers and contractors in active construction stages. Literature is devoid of a well-defined decision-making matrix that uses the local expert judgment to rate, prioritize, and implement the use of hard, soft, and hybrid structures (e.g., seawalls, revetments, riprap, breakwaters, and mangroves) based purely on the quantitative risk matrix of low, moderate, and high erosion risks.

This research directly addresses these shortcomings by creating an integrated Construction Management Framework for Shoreline Protection Structures that is specific to the unique and dynamic nature of Aparri, Cagayan’s estuary environment. As opposed to simply creating a static risk assessment, this research integrates both the quantified GIS-based End Point Rate risk levels and qualitative expert analysis through the use of an explicit multi-criteria decision matrix. This Framework divides the construction process into specific, manageable phases from the beginning to the end of the project life cycle, including site evaluation, selection of a risk matched structure, localized design considerations, and long-term maintenance.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	33

## CHAPTER III METHODOLOGY

The methods and processes that will be applied in conducting the research will be presented in this chapter. The description of the processes is systematic and replicable in order to allow any other researcher to repeat the process. The methodologies have been developed considering the aims of the research such as assessing and classifying the risk of erosion, assessing and ranking the shore protection structures, and managing the construction of the structures.

### General Overview

This research study will adopt a mixed-method research design, which incorporates both qualitative and quantitative research methods in order to develop an effective construction management framework for shoreline protection structures in selected areas of Aparri, Cagayan. Quantitative methods will be employed in computing shoreline change rates, classifying coastal erosion risk levels using GIS, and analyzing expert evaluations of shoreline protection structures through weighted mean. Qualitative information from field observations and secondary data will be used to support the interpretation of shoreline conditions and the development of the proposed framework.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	34

The use of the mixed method is justified by its ability to provide insights on both

aspects.

### Study Area

The study will be conducted in eight barangays of Aparri, namely Linao, Maura, Punta, San Antonio, Bulala Sur, Bulala Norte, Dodan, and Paddaya. These barangays share one continuous shoreline and are influenced by the same coastal processes including wave action, storm surges, and monsoon winds.

Figure 1. Map of Aparri, Cagayan

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	35

### Research Design

The design used in this study would be a mixed method approach involving qualitative and quantitative methods to develop a construction management framework for shoreline protection structures in selected areas of Aparri, Cagayan by considering the factors causing coastal erosion and the risk classification for such erosion. The use of this type of research design is justified since the investigation requires both qualitative and quantitative methods to assess the coastal area and evaluate the alternative shoreline protection structures.

Quantitative analysis will be used to compute shoreline change rates and classify erosion risk levels using GIS.

Quantitative analysis will involve the determination of the risk level of coastal erosion as low, medium, and high. It will also include the evaluation, comparison, and ranking of alternative shoreline protection structures based on expert opinion and weighted means. The findings from the analysis will provide a basis for recommending the most appropriate shoreline protection structures under different erosion risks.

The results of both parts will be combined into a construction management framework for shoreline protection structures customized for the local environment of selected parts of Aparri, Cagayan. This ensures that the output is both data-informed and grounded on expert evaluation, making it applicable for coastal management and engineering practice.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	36

### Population and Sample

The target respondents of the research project are those with specific knowledge and experience with regard to coastal engineering, construction management, and shoreline protection techniques. These consist of licensed civil engineers, coastal or environmental engineers, contractors, as well as technical persons from local government units (LGUs) concerned with planning and implementing coastal projects.

A purposive sampling method will be used in choosing the respondents of the research project. With such a sampling technique, only those qualified and knowledgeable about shore erosion and shore protection will be selected for the study. The qualifications and experiences of the respondents will take into account their professional backgrounds and familiarity with the issues at hand.

The total number of respondents is not specified since this is determined by the availability and readiness of the said respondents. Collection of data will stop once enough information will have been gathered regarding the shore protection structure being assessed in the study.

### Research Instrument

The following research instruments will be employed in order to acquire all the data required for creating a management framework for construction of structures for protection against coastal erosion in selected areas of Aparri, Cagayan. Such research instruments have been chosen to suit the objectives of the research study in relation to classifying risks, and assessing shoreline protection structures. The observations will be used to provide supporting information for interpreting erosion risk classification results.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	37

The Geographic Information Systems (GIS) will be employed for processing the spatial data as well as calculating the rate of erosion in all the shoreline areas that have been selected. The field data and spatial references (shoreline locations and previous data for the coasts if available) will be encoded in the GIS system, and the shoreline changes will be determined to calculate the shoreline change rate in meters per year.

Third, an Evaluation Questionnaire will be constructed to collect information from professionals who have been identified as civil engineers, coastal or environmental engineers, and LGU technical staff. Information will be collected through the analysis of the efficiency and feasibility of different structures used for shoreline protection. The expert evaluation will be measured using a Likert scale and will later be analyzed using the weighted mean technique.

Lastly, secondary data will be collected using various maps, reports about coastal areas, and other literature. These tools help collect data that will serve as a basis for validating the results of field observations.

### Data Gathering Procedure

Prior to the actual conduct of the study, the researchers will obtain a letter of endorsement from the research adviser and the Dean of the College of Engineering and Architecture. Upon obtaining the letter of endorsement, permission letters will be obtained to DENR,MDRRMO,DPWH, LGU of Aparri, among others for the collection of the required secondary data and field observations in the selected coastal barangays.

With proper permissions having been sought and obtained, the secondary data required in this study will be collected once the necessary permissions have been acquired

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	38

for this research. Secondary data to be collected will include historical shoreline maps, satellite images, Geographic Information System (GIS) data, and government records concerning the condition of the shorelines of Aparri, Cagayan. Satellite images of the years 1990, 2000, 2010, 2020, and 2025 will be considered in order to gather past and present positions of the shorelines in the study area.. These secondary data will serve as the basis for the determination of the changes in the shoreline and assessing coastal erosion risk levels.

The process of conducting field observations will take place after the gathering of secondary data in selected coastal barangays. In this phase, the researchers will conduct their observations and record the current conditions of the shorelines using pictures, observation checklist, and site inspection. The information obtained from the field observations will be used to supplement the secondary data by documenting the current shoreline conditions in the selected coastal barangays.

Once the field observation has been completed, the researchers will prepare an evaluation questionnaire for the expert respondents. Before conducting the actual survey, the research instrument will undergo pilot testing to test its reliability. Revision will be done depending on the result of the pilot test.

Upon finalizing the questionnaire, the said tool will be handed out to the chosen respondents using purposive sampling. The respondents shall comprise registered civil engineers, DPWH engineers, coastal or environmental engineers, contractors, and LGU technical personnel who have adequate background and experience in shoreline protection works. Before filling out the questionnaire, the objective of the research shall be explained

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	39

to the respondents. And their voluntary involvement shall be solicited from them. It is also necessary to assure them that all the information obtained shall be treated confidentially and shall only be used in academic purposes.

After the retrieval of all the questionnaires, the researchers shall consolidate and compile the accomplished questionnaires together with the secondary data and field observation notes. The collected data will be processed and analyzed to classify the coastal erosion risk levels, rate and prioritize the shoreline protection structures based on expert opinion, and propose the construction management approach for shoreline protection structures in Aparri, Cagayan.

### Risk Assessment Method

The risk assessment of coastal erosion will be done using the information from historical maps of the shoreline, the satellite image data, Geographic Information System (GIS), and other governmental data that will be collected as part of the data collection process. Satellite imagery data of the years 1990, 2000, 2010, 2020, and 2025 will be analyzed to find out the position of the shoreline both historically and recently in the chosen coastal barangays of Aparri, Cagayan. Through shoreline mapping and change detection, the position of the shoreline in these years will be digitized and overlaid.

The selected years provide multi-temporal shoreline positions covering a long-term period from 1990 to 2025. The 1990 shoreline will serve as the earliest reference position, while the 2025 shoreline will represent the most recent shoreline

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	40

position. The 2000, 2010, and 2020 shoreline positions will provide intermediate observations of shoreline movement and changes over time.

In terms of the overall long-term assessment of shoreline changes, the EPR will be determined by taking the shoreline position in 1990 as the earlier shoreline position and that in 2025 as the later shoreline position. The shoreline positions in 2000, 2010, and 2020 will be taken as the intermediate shoreline positions for visualizing the temporal change in shoreline movement. The shoreline change rate will be computed using the following formula:

(𝑆 −𝑆 )

𝑇

Erosion Rate =   2	1

where:

S2 = shoreline position in the later year S1 = shoreline position in the earlier year T = time interval in years

A negative value suggests erosion, while a positive one represents accretion. The unit of measurement is meters per year (m/yr).

Based on the computed shoreline change rates, each shoreline segment will be classified into low, medium, and high coastal erosion risk levels using the adopted classification criteria presented in Table 3.1.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	41

Table 3.1. Classification of Coastal Erosion Risk Level

| Risk Level | Erosion Rate |
| --- | --- |
| Low | < 2 m/year |
| Medium | 2-5 m/year |
| High | > 5 m/year |

Note: Classification thresholds were adapted from coastal geomorphology studies

Upon classification of the shorelines, the classified information shall then be used in the generation of the coastal erosion risk map using the Geographic Information System (GIS). The resulting map will indicate the spatial location of low, medium, and high-risk coastal areas within the selected barangays of Aparri, Cagayan.

From the generated coastal erosion risk map, an evaluation and ranking of the appropriate shoreline protection structures will be performed considering the level of coastal erosion risk. The findings from the evaluation process will be used in the development of the proposed construction management framework for the shoreline protection structures.

For the purpose of this study, coastal erosion risk level is operationally classified based on the computed shoreline change rate. This classification provides a spatial basis for identifying and prioritizing shoreline areas for protection planning within the study area and does not represent a comprehensive assessment of exposure or vulnerability.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	42

### Evaluation and Ranking of Shoreline Protection Structures

After determining the risks of coastal erosion, the rating of the shoreline protection structures identified will then follow so that the best alternative will be determined based on the risk level associated with the coastal erosion. This will be guided by the result of the coastal erosion risk assessment as well as the site conditions in the selected coastal barangays of Aparri, Cagayan.

An expert evaluation questionnaire will then be issued to some respondents which include licensed civil engineers, coastal or environmental engineers, contractors, and LGU technical staff knowledgeable in shoreline protection. The respondents will be asked to rate each of the shoreline protection structures in terms of stability, effectiveness, cost of construction, durability, maintenance requirements, and environmental impact. This is because the aforementioned factors play a great role in the determination of the best shoreline protection structures in Aparri, Cagayan.

The data to be collected via the use of the expert evaluation questionnaire will undergo analysis using the weighted mean technique to determine the average score of each of the shoreline protection structures according to evaluation criteria. Once the data have been analyzed using the weighted mean, the resulting scores will be put on the decision matrix to allow for comparison of the various shoreline protection structures. These scores will then be ranked such that the shoreline protection structure with the highest score is the most appropriate alternative.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	43

These outputs from the evaluation and ranking process will form one of the important inputs in the construction of the proposed Construction Management Framework for shoreline protection structures in Aparri, Cagayan.

Table 3.2 Decision Matrix for the Evaluation and Ranking of Shoreline Protection Structures

| Shoreline Protection Structure | Stabili ty | Effect ivenes s | Cost of Constr uction | Dura bility | Mainten ance Require ments | Environ mental Impact | Overal l Score | Ran k |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Seawall |  |  |  |  |  |  |  |  |
| Revetment |  |  |  |  |  |  |  |  |
| Riprap |  |  |  |  |  |  |  |  |
| Breakwater |  |  |  |  |  |  |  |  |
| Mangrove Rehabilitati on |  |  |  |  |  |  |  |  |

These shoreline protection structures shall then be ranked based on their overall scores. The alternative with the highest overall scores shall be regarded as the most suitable shoreline protection structure in relation to the degree of the coastal erosion risks. This ranking process shall form the foundation for the creation of the proposed construction management framework for shoreline protection structures in Aparri, Cagayan.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	44

### Framework Development Process

Construction Management Framework for Shoreline Protection Structures in Aparri, Cagayan can be established through incorporating the findings from the coastal erosion risk assessment and the evaluation and ranking of shoreline protection structures. The outputs of the coastal erosion risk assessment and the Decision Matrix will be used to formulate the framework which is essential in determining the proper approach to use in the selection and implementation of the proper shoreline protection structures in the chosen coastal barangays of Aparri, Cagayan.

The framework can be established by organizing the construction management phases including project planning, site evaluation, selecting appropriate shoreline protection structure, design considerations, construction implementation, monitoring, inspection, and maintenance of the structure. The above mentioned phases are useful in ensuring that there will be a systematic process of determining the proper shoreline protection measures depending on the coastal erosion risk levels and site condition.

Flowchart of the framework can be created in order to identify the processes to be undertaken in establishing the proposed Construction Management Framework for Shoreline Protection Structures in Aparri, Cagayan.

It is anticipated that the proposed Construction Management Framework will be used as an effective tool by the local government units, engineers, planners, and other interested parties in designing, implementing, evaluating, and maintaining the coastal erosion prevention structures in Aparri, Cagayan.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	45

Figure 2. Proposed Construction Management Framework

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	46

### Reliability Test

The reliability of the research tools which will be used in this study will also be ensured to guarantee the consistency and reliability of the information to be collected in the construction management framework for the shoreline protection structures in Aparri, Cagayan in terms of factors associated with coastal erosion and risk categorization.

For the Field Observation Checklist, the reliability of the tool will be maintained by conducting various consistencies of the observations. The research team will observe different sites multiple times and validate the coastal erosion factors including waves, sediments, and coastal development in order to maintain the consistency of the observations.

For the GIS-based erosion rate computation, reliability can be ensured through the cross-checking of the spatial data as well as the repeated processing of these. Multiple processing of the spatial inputs will help ensure that there will be no variation in the results when it comes to the calculated coastal erosion rates. Secondary spatial sources and coastal data may also be considered for verifying the results obtained through the use of GIS.

For the Expert Evaluation Questionnaire, reliability can be ensured through the use of a Likert scale questionnaire to be distributed among chosen experts like civil engineers, coastal or environmental engineers, and LGU technical staff members. Reliability will be measured using Cronbach’s Alpha to determine the reliability of the Likert scale questionnaire used for assessing shore protection structures according to their  stability,

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	47

effectiveness,	cost	of	construction,	durability,	maintenance	requirements,	and environmental impact.

The Cronbach’s Alpha coefficient will be computed using the following formula:

α =

𝑘

𝑘−1

2

Σ σ

2

(1 − 	𝑖 )

σ

𝑖

Where:

α = Cronbach’s Alpha

𝑘 =

number of questionnaire items

σ

2 = variance of each item

𝑖

σ

2 = total variance of the overall score

𝑖

A pilot test will be conducted among selected respondents prior to the final data gathering. A Cronbach’s Alpa value of 0.70 will be considered acceptable, indicating that the questionnaire has a good internal consistency and is reliable for expert evaluation.

The above-mentioned means to ensure reliability of measurement instruments are expected to contribute to the reliability of the research instruments to be used.

### Statistical Tools and Treatment

The study will utilize various tools of analysis and statistics to interpret the results of the data collected and to support the objectives of the research.

### Descriptive Statistics

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	48

Descriptive statistical analysis will be used to summarize the computed shoreline erosion rates and classify shoreline segments according to their level of erosion risk. The findings will then be depicted through tables, maps, and graphs to demonstrate the spatial variability of shoreline evolution within the study area.

### GIS Spatial Analysis

The Geographic Information System (GIS) was utilized to map the shoreline change and analyze the spatial distribution of shoreline erosion. This tool will be useful in visualizing areas prone to shoreline erosion.

### Shoreline Change Rate Analysis

Shoreline change rate analysis will be utilized to assess the level of coastal erosion or accretion in Aparri, Cagayan. Shoreline change rate analysis measures the changes in shoreline position between two different periods of time using satellite imagery. Shoreline erosion or accretion rates are calculated using the following formula:

(𝑆 −𝑆 )

𝑇

Erosion Rate =   2	1

where:

S2 = shoreline position in the later year S1 = shoreline position in the earlier year T = time interval in years

Results of this analysis will be expressed as rates of shoreline changes in meters/year. Negative values indicate erosion, whereas positive values indicate accretion.

### Frequency Count

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	49

This statistical method was employed to characterize the number of respondents in each category based on their professional background and involvement in shoreline protection projects in Aparri, Cagayan. It will provide a clear description of the distribution of respondents and support the interpretation of their assessments of the shoreline protection structures based on stability, effectiveness, cost of construction, durability, maintenance requirements, and environmental impact.

### Weighted Mean

Analysis of the gathered data from the expert assessment survey questionnaire will involve using the weighted mean method, whereby we shall calculate the average score given by the experts with regards to the efficiency and feasibility of construction of the shoreline protection structures in Aparri, Cagayan.

𝑁

Weighted Mean Formula:

𝑥 =  Σ𝑓𝑥

Where:

𝑥 = weighted mean

f = frequency response x = scale value

N = total number of response

The resulting weighted means will be entered in the Decision Matrix for the comparison and ranking of shoreline protection alternatives. The best alternative from among those will be the one that has the highest weighted means of the scores assigned.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	50

Interpretation Scale

The scale below will be utilized in interpreting the results of the weighted mean scores of the experts' evaluation:

| Scale | Description | Range | Interpretation |
| --- | --- | --- | --- |
| 5 | Highly Appropriate | 4.21-5.00 | Very High |
| 4 | Appropriate | 3.41-4.20 | High |
| 3 | Moderately Appropriate | 2.61-3.40 | Moderate |
| 2 | Slightly Appropriate | 1.81-2.60 | Low |
| 1 | Not Appropriate | 1.00-1.80 | Very Low |

### Frequency and Percentage Distribution

For frequency and percentage distribution, the composition of expert respondents according to their professional background (i.e., civil engineers, environmental engineers, contractors, and LGU technical personnel) will be presented. Frequency pertains to the number of respondents within each category, whereas percentage is the ratio of each

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	51

respondent category against the total number of respondents. This descriptive statistic would help identify the expertise distribution of the respondents in the evaluation study.

### Ethical Consideration

The study will be done according to ethical principles that will ensure credible and responsible research in the creation of a construction management framework for shoreline protection structures in Aparri, Cagayan. Coordination with the proper Local Government Units and other concerned agencies will be done before proceeding with data gathering. Activities in the field will conform to current rules and will not intrude into the environment and people in the area.

Respondents such as engineers and technical specialists will participate in the research voluntarily. Informed consent will be sought, and the goals of the study and the part played by participants will be clearly stated. All information will be kept private and respondents will be assured of anonymity. The results of the data collected from fieldwork, GIS analysis, and expert opinions will be correctly recorded, safely stored, and only used for academic purposes without distortion.

Secondary sources of information will be cited appropriately to uphold academic integrity. Only authentic and ethically obtained information will be utilized. Being an engineering recommendation, the management framework to be created will be presented as a decision-making tool and not a finalized design.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	52

## CHAPTER IV

## RESULTS AND DISCUSSION

This chapter presents the findings of the study and interprets them in relation to the objectives and literature reviewed.

### 4.0 Introduction

The findings of the study, which will be discussed in the following section of the chapter, are derived according to the objectives of the research. These include the identification of coastal erosion risk levels, assessment of shoreline protection structure, ranking of suitable shoreline protection structures, and construction management framework for shoreline protection structures in Aparri, Cagayan. The findings of the research are derived from GIS analysis of the shoreline, secondary information from relevant agencies, field observations, and the assessment of the expert respondents.

### Classification of Coastal Erosion Risk

The first objective of the study was the classification of the coastal erosion risk of the selected coastal barangays of Aparri, Cagayan into Low, Medium, and High. In relation to the methodology, the classification of the risk level is dependent upon the analysis of the historical shoreline position utilizing satellite images, GIS, and shoreline change detection.

Shoreline positions of the years 1990, 2000, 2010, 2020, and 2025 were analyzed to determine the temporal and spatial changes in shoreline position. The shoreline of 1990 was considered as the earliest reference position while that of 2025 was taken as the latest

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	53

position. The shorelines of 2000, 2010, and 2020 were taken as intermediate positions to depict the changes in shoreline position over time.

The results of the analysis are depicted in the form of two maps: (1) Multi-Temporal Shoreline Change Map and (2) Coastal Erosion Risk Map. The first map shows the movement of the shoreline in all five years of observation, whereas the latter map shows the classification of shoreline segments based on their erosion rate.

### Multi-Temporal Shoreline Change

The multi-temporal shoreline analysis was conducted to visualize the changes in shoreline position within the selected coastal barangays of Aparri, Cagayan from 1990 to 2025.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	54

Figure 4.1. Multi-Temporal Shoreline Change Map of Selected Coastal Barangays in Aparri, Cagayan

The map presents the shoreline positions for 1990, 2000, 2010, 2020, and 2025 using different line colors. The eight selected coastal barangays included in the analysis are Bulala Sur, Bulala Norte, Linao, Punta, San Antonio, Maura, Dodan, and Paddaya.

According to Figure 4.2, the position of the shorelines is different from one another within the study area, which means that there is a spatial variation in the position of the shorelines after 35 years of observations. The differences in the position of the shoreline can be seen in some parts of the coastline area, especially in the western part of the study area and the coast that goes towards Punta, San Antonio, Maura, Dodan, and Paddaya.

The combination of the shoreline positions shows a graphical presentation of the movement and direction of the shorelines throughout the period of observation. Parts wherein the shoreline positions are apart mean that the shoreline experiences larger movement compared to other parts wherein shoreline positions are still near each other.

However, the visual difference in the positions of shoreline was not the only basis in determining the Low, Medium, and High erosion risk classification. Following the procedure of the study, the overall shoreline change rate was calculated using the EPR.

### Computation of Shoreline Change Rate

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	55

To quantify the long-term shoreline movement, the End Point Rate (EPR) was determined using the shoreline positions for 1990 and 2025.

The shoreline change rate was calculated using the following formula:

(𝑆 −𝑆 )

𝑇

EPR =   2	1

where:

S₂ = shoreline position in the later year (2025) S₁ = shoreline position in the earlier year (1990)

T = time interval between the two shoreline positions

For this study, the time interval between 1990 and 2025 was 35 years.

The EPR generated is measured in meters per year (m/year). If the EPR is negative, it shows that there is shoreline movement due to erosion. However, if the EPR is positive, it shows accretion. Intermediate shoreline locations for 2000, 2010, and 2020 were kept to show the shoreline changes visually, whereas 1990 to 2025 was used to assess the long-term EPR.

The shoreline change rates obtained have been categorized according to three erosion risks levels using threshold values as determined by the methodology.

Table 4.1. Classification of Coastal Erosion Risk Level

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	56

| Risk Level | Erosion Rate |
| --- | --- |
| Low | < 2 m/year |
| Medium | 2–5 m/year |
| High | > 5 m/year |

Source: Osondu, I., Imoni, O., Chukwuemeka, P., et al. (2025). Machine learning-based shoreline change prediction and erosion analysis: a case study of Ogu/Bolo, Nigeria.

Discover Civil Engineering, 2, 230.

The classification was applied to the shoreline segments based on their computed erosion rates. Therefore, the classification represents the spatial condition of the shoreline segments rather than automatically assigning one risk category to the entire barangay.

### Barangay-Level EPR and Coastal Erosion Risk Results

Table 4.2 presents the EPR results and the corresponding risk-area statistics for the eight selected coastal barangays. The table includes the mean EPR, minimum EPR, maximum EPR, and the computed areas under Low, Medium, and High Risk.

Table 4.2 Barangay-Level EPR and Coastal Erosion Risk Results, 1990–2025

| Barangay | Mean EPR (m/year) | Minimum EPR (m/year) | Maximum EPR (m/year) | Low Risk (ha) | Medium Risk (ha) | High Risk (ha) |
| --- | --- | --- | --- | --- | --- | --- |
| Dodan |  |  |  |  |  |  |

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	57

| Maura |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Bulala Norte |  |  |  |  |  |  |
| San Antonio |  |  |  |  |  |  |
| Linao |  |  |  |  |  |  |
| Paddaya |  |  |  |  |  |  |
| Punta |  |  |  |  |  |  |
| Bulala Sur |  |  |  |  |  |  |

### Coastal Erosion Risk Map

The computed EPR values were used to generate the Coastal Erosion Risk Map shown in Figure 4.2. The map spatially presents the classified shoreline areas according to the adopted erosion-rate thresholds.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	58

Figure 4.2. Coastal Erosion Risk Map of Selected Coastal Barangays in Aparri, Cagayan

The map presents the spatial distribution of the three coastal erosion risk levels using different colors. Green represents Low Risk (<2 m/year), yellow-orange represents Medium Risk (2–5 m/year), and red represents High Risk (>5 m/year). These classifications follow the thresholds specified in the study methodology.

Based on Figure 4.2, the coastal erosion risk within the study area is spatially variable. The shoreline does not exhibit one uniform risk classification throughout the eight selected coastal barangays. Instead, Low, Medium, and High Risk classifications occur along different shoreline segments.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	59

The High Risk category, as shown by the red color along the shoreline segments, is evident in some portions of the western coastal stretch of the study site, such as Bulala Sur and Bulala Norte. These red-colored shoreline portions have erosion rates that exceed 5 m/year, as per the classification criteria provided in the methodology. The Medium Risk category, as depicted by the orange shoreline portions, is evident in some portions of the study site, such as Bulala Norte, Punta, San Antonio, Maura, Dodan, and Paddaya. These shoreline portions indicate erosion rates falling in the classification range of 2-5 m/year.

The Low Risk category, as illustrated by the green shoreline segments, is evident in some portions of the study site, such as Linao and others shown as green segments in the figure. These portions are characterized by shoreline erosion rates below 2 m/year.

From the distribution of the three categories, it can be seen that there are variations in terms of the level of coastal erosion along the study site. This, thus, gives a spatial context upon which to base further analysis in the succeeding stages of the study.

### Discussion of the Coastal Erosion Risk Map

The Coastal Erosion Risk Map offers a spatial representation of the shoreline change findings from the multi-temporal analysis process. The map represents the results of the shoreline change rates in terms of three risk groups, enabling visualization of the areas with various degrees of shoreline erosion.

The red-colored shoreline segments are those segments that have been classified under High Risk with an erosion rate exceeding 5 meters per year. They are located along

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	60

the western coast, especially at Bulala Sur and Bulala Norte. It is clear that greater amounts of shoreline changes were observed in these segments of the area under study. The yellow-orange colored shoreline segments are those that have been classified under Medium Risk, with erosion rates of 2–5 meters per year. They have been observed along several portions of the coastline from the western coast toward the eastern coast barangays. Green segments of the coastline denote the Low Risk areas that refer to those shoreline sectors with erosion rate under 2 m/year. Their selective location indicates that different shoreline segments underwent different levels of change.

At the same time, the comparison of figures 4.1 and 4.2 shows the connection between shoreline change and its erosion risk classification. Figure 4.1 shows the temporal picture of shoreline locations, whereas Figure 4.2 gives the final classification according to shoreline change rate. Consequently, these two pictures play different but equally important roles in the assessment process. It is vital to underline that coastal erosion risk classification in this research is technically based on the shoreline change rate. The task of the classification is to give a spatial background for selection of the shorelines to be protected. It is not a full assessment of the risk from any perspective.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	61

### Profile of the Expert Respondents

In this section, the profiles of the expert respondents who give their professional assessment of the various structures that protect shorelines are presented. These respondents are classified based on their profession and experience.

Table 4.1. Professional Background of the Expert Respondents

| PROFESSIONAL BACKGROUND | FREQUENCY | PERCENTAGE |
| --- | --- | --- |
| Civil Engineer | 21 | 38.9% |
| DPWH Engineer | 18 | 33.3% |
| Coastal/Environmental Engineer | 12 | 22.2% |

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	62

| Contractor | 1 | 1.9% |
| --- | --- | --- |
| LGU Technical Personnel | 2 | 3.7% |
| Total | 54 | 100% |

Table 4.1 below reflects the professional background of the 54 expert respondents who took part in the research. The largest group comprises Civil Engineers – 21 respondents or 38.9% of the total number of respondents. Next comes DPWH Engineers with 18 respondents or 33.3%, followed by Coastal/Environmental Engineers with 12 respondents or 22.2%. There is 1 Contractor respondent or 1.9% and 2 LGU Technical Personnel respondents or 3.7%.

It should be noted that the composition of respondents makes it possible to get the views of experts having experience in different fields of engineering and technical expertise pertinent to shoreline protection and construction management.

Table 4.2. Years of Professional Experience of the Expert Respondents

| YEARS OF EXPERIENCE | FREQUENCY | PERCENTAGE |
| --- | --- | --- |
| Less than 5 years | 29 | 53.7% |
| 5–10 years | 16 | 29.6% |
| 11–20 years | 6 | 11.1% |
| More than 20 years | 3 | 5.6% |
| Total | 54 | 100% |

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	63

Table 4.2 shows the years of experience of the experts as respondents. The greatest number of respondents is those who have less than 5 years of experience, amounting to 29 respondents or 53.7%. Next is 5-10 years of experience for 16 respondents or 29.6%. There are 6 respondents or 11.1% with 11-20 years of experience, while there are 3 respondents or 5.6% with more than 20 years of experience.

From the distribution above, it can be seen that the respondents are both experienced and very experienced individuals. Their backgrounds and years of experience give different viewpoints when evaluating the shore protection structures being studied.

Table 4.3. Respondents’ experience, familiarity, and training related to Shoreline Protection Structures

| QUESTION | RESPONSE | FREQUENCY | PERCENTAGE |
| --- | --- | --- | --- |
| Have you worked on or supervised a Shoreline Protection Structures? | Yes | 15 | 27.8% |
|  | No | 39 | 72.2% |
| Total |  | 54 | 100.0% |
| Are you familiar with different types of Shoreline Protection Structures (Seawalls, Revetments, Riprap, Breakwater, Mangrove Rehabilitation)? | Yes | 49 | 90.7% |
|  | No | 5 | 9.3% |
| Total |  | 54 | 100.0% |

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	64

| Have you received any education or training related to Coastal Engineering or Shoreline Protection? | Yes | 21 | 38.9% |
| --- | --- | --- | --- |
|  | No | 33 | 61.1% |
| Total |  | 54 | 100.0% |

Table 4.3 presents the frequency and percentage distribution of the 54 respondents based on their experience, familiarity, and education/training related to the shoreline protection structure. The results show that familiarity with different types of shoreline protection structures has the highest proportion with 49 respondents (90.7%) answering yes, indicating that majority of respondents are familiar with structures such as seawalls, revetments, riprap, breakwaters, and mangrove rehabilitation. This is followed by respondents who have received education related to Coastal Engineering or Shoreline Protection, with 21 respondents (38.9%) answering yes. Meanwhile, 15 respondents (27.8%) answered that they have worked on or supervised shoreline protection structures.

By contrast, 39 respondents (72.2%) indicated that they have not worked on or supervised shoreline protection structures, while 33 respondents (61.1%) have not received education or training related to Coastal Engineering or Shoreline Protection. Only 5 respondents (9.3%) answered that they are not familiar with different types of shoreline protection structures. These findings indicate that although direct work experience and formal education or training among the respondents are relatively limited,

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	65

most respondents have sufficient familiarity with different shoreline protection structures, which provides relevant background for their assessment in succeeding parts of the study.

### Evaluation of Shoreline Protection Structures

The structures considered in the study include seawalls, revetments, riprap, breakwater, and mangrove rehabilitation. These structures were evaluated by selected experts based on criteria such as stability, effectiveness, construction cost, durability, maintenance requirements, and environmental impact. The evaluation was conducted using a Likert-scale questionnaire. The responses were analyzed using the to determine the average assessment for each shoreline protection structure. The resulting scores were then entered in a decision matrix for comparison and ranking.

Table 4.4. Weighted Mean Evaluation of Shoreline Protection Structures

| DECISION MATRIX |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Shoreline Protection Structures | Stability | Effecti-veness | Cost | Durabi-lity | Mainte-nance | Environ-mental Impact | Overall Mean | Inter-p retatio n | Rank |
| Seawall | 4.5370 | 4.5741 | 4.2778 | 4.2037 | 4.2963 | 4.2037 | 4.3488 | Very High | 1 |
| Revetment | 4.2593 | 4.1296 | 3.9074 | 3.7593 | 4.0000 | 3.8704 | 3.9877 | High | 3 |
| Riprap | 3.8148 | 3.5741 | 3.5741 | 3.3704 | 3.8148 | 3.6111 | 3.6265 | High | 5 |
| Breakwater | 3.8519 | 3.8149 | 3.6667 | 3.4630 | 3.7963 | 3.6481 | 3.7068 | High | 4 |
| Mangrove Rehabilita-tion | 4.0185 | 4.1667 | 4.3519 | 3.8889 | 3.9074 | 4.4815 | 4.1358 | High | 2 |

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	66

Table 4.4 highlights the weighted mean evaluation of the different shoreline protection structures based on stability, effectiveness, cost, durability, maintenance, and environmental impact. The findings show that seawall is the highest rated shoreline protection structure, with an overall mean of 4.3488 signifying the highest perceived suitability among the structures evaluated. This is followed by mangrove rehabilitation, which obtained an overall mean of 4.1358, ranking second. The revetment ranked third with an overall mean of 3.9877, followed by breakwater with overall mean of 3.7068, while riprap obtained the lowest overall mean of 3.6265, ranking fifth.

Among the individual criteria, seawall received the highest weighted mean for maintenance (4.2963), durability (4.2037), effectiveness (4.5741) and stability (4.5370), indicating that the respondents perceived it as highly effective and stable for shoreline protection. In contrast, mangrove rehabilitation received the highest rating for environmental impact and (4.4815) and cost (4.3519), suggesting favorable perceptions regarding its environmental and cost- related aspects. The results further show that the rating varied across the criteria, indicating that each shoreline protection structure has different perceived strengths in terms of stability, effectiveness, cost, durability, maintenance, and environmental impact.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	67

## CHAPTER V

## CONCLUSION AND RECOMMENDATION

This chapter summarizes the study, presents conclusions based on the findings, and offers recommendations for practice, policy, or future research.

### Summary

Provide a concise recap of the study’s purpose, methodology, and major findings.

This should be written in paragraph form, not as bullet points.

### Conclusion

State the conclusions drawn directly from the results. Each conclusion should clearly answer the research objectives. Avoid introducing new data here.

### Recommendations

Offer practical or theoretical recommendations based on the conclusions. These may include suggestions for institutions, practitioners, policymakers, or future researchers. Recommendations should be specific, actionable, and logically derived from the findings.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	68

## REFERENCES

All sources cited in the manuscript must be listed in the References section, formatted according to APA style (7th edition). In-text citations should follow the author–date format, while the reference list must be arranged alphabetically by the first author’s surname, single-spaced, and formatted with a hanging indent. Journal titles are italicized, volume numbers included, and DOI links provided when available. Hypothetical examples are as follows (for template purposes only):

Dela Rosa, A. (2025, March 15). Local universities expand sustainability initiatives. The Philippine	Daily	Chronicle. https://www.philchronicle.ph/news/sustainability-initiatives

GreenFuture Organization. (2025). Climate action projects in Southeast Asia. Retrieved February 10, 2026, from https://www.greenfuture.org/projects

Lopez, F. G. (2021). Assessing water management practices in rural communities

(Unpublished undergraduate thesis). Cagayan State University, Carig Campus.

Ramirez, J. P. (2022). Foundations of research methodology: A practical guide (2nd ed.).

Manila Academic Press.

Santos, R. L., & Cruz, M. T. (2024). Renewable energy adoption in urban communities: A comparative study. Journal of Sustainable Development Studies, 18(2), 45–62. https://doi.org/10.1234/jsds.2024.5678

Villanueva, K. M. (2023). Smart building technologies for tropical climates. In Proceedings of the International Conference on Sustainable Engineering (pp. 112–120). Singapore Institute of Technology.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	69

## APPENDICES

### Appendix A. Guide to Appendices

The appendices provide supplementary material that supports the study but is too detailed or lengthy to include in the main text. Each appendix should be labeled clearly, using the format “Appendix A. Title/Description” or “Appendix B. Title/Description”, with the content following immediately after the label and title. Appendices must be referenced in the body of the manuscript where relevant, and they should contain materials such as survey instruments, raw data tables, sample calculations, extended descriptions of procedures, or supplementary figures and diagrams.

Figures, tables, and equations included in the appendices must have numbering that is separate from the main text. To distinguish them, use the appendix letter as a prefix. For example, figures in Appendix A should be labeled as Figure A1, Figure A2, and so on, while tables should be labeled as Table A1, Table A2, and equations as (A1), (A2). In Appendix B, numbering would continue as Figure B1, Table B1, and (B1), respectively.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	70

### Appendix B. Typical Appendix Contents

Typical contents for the appendices may include:

- Copies of survey questionnaires or interview guides

- Raw data tables or extended datasets

- Sample calculations or derivations

- Detailed descriptions of instruments or procedures

- Additional figures, charts, or diagrams not central to the main discussion Appendices should be formatted consistently, with clear titles and stand-alone

descriptions.	They	serve	as	supporting	evidence	and	documentation,	ensuring transparency and replicability without interrupting the flow of the main chapters.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	71

## REFERENCES

Tsiakos, C. A. D., & Chalkias, C. (2023). Use of machine learning and remote sensing techniques for shoreline monitoring: a review of recent literature. Applied Sciences, 13(5), 3268.

https://scholar.google.com/scholar?hl=en&as_sdt=0%2C5&q=Use+of+Machine+Learning

+and+Remote+Sensing+Techniques+for+Shoreline+Monitoring%3A+A+Review+of+Rec ent+Literature&btnG=#d=gs_qabs&t=1783038384408&u=%23p%3Do7Bo4JbSpi8J

Cavalli, R. M. (2024). Remote data for mapping and monitoring coastal phenomena and parameters: A systematic review. Remote Sensing, 16(3), 446. https://scholar.google.com/scholar?hl=en&as_sdt=0%2C5&q=Remote+Data+for+Mappin g+and+Monitoring+Coastal+Phenomena+and+Parameters%3A+A+Systematic+Review& btnG=#d=gs_qabs&t=1783039196865&u=%23p%3DPruwnhVcstcJ

Sun, W., Chen, C., Liu, W., Yang, G., Meng, X., Wang, L., & Ren, K. (2023). Coastline extraction using remote sensing: A review. GIScience & Remote Sensing, 60(1), 2243671. https://scholar.google.com/scholar?hl=en&as_sdt=0%2C5&q=Coastline+extraction+using

+remote+sensing%3A+a+review&btnG=#d=gs_qabs&t=1783039631304&u=%23p%3Dy WgH_lePG7EJ

Nerves, A., Rivera, F. D., Blanco, A., Tirol, Y., & Nadaoka, K. (2024). Shoreline Change Analysis in New Washington, Aklan using Digital Shoreline Analysis System (DSAS).

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	72

ISPRS Annals of the Photogrammetry, Remote Sensing and Spatial Information Sciences, 10, 111-117.

https://doi.org/10.5194/isprs-annals-X-5-2024-111-2024

Felipe, A. J. B., Alejo, L. A., Padre, R. J., & Bareng, J. L. R. (2026). Past and future river bank trend assessment of lower Cagayan River, Philippines. Environment, Development and Sustainability, 28(2), 3363-3398.

https://link.springer.com/article/10.1007/s10668-024-05113-3

Woodroffe, C. D., Evelpidou, N., Delgado-Fernandez, I., Green, D., Sengupta, D., Karkani, A., & Ciavola, P. (2025). Coastline changes: A reconsideration of the prevalence of recession on sandy shorelines. Cambridge Prisms: Coastal Futures, 3, e18. https://www.cambridge.org/core/journals/cambridge-prisms-coastal-futures/article/coastlin e-changes-a-reconsideration-of-the-prevalence-of-recession-on-sandy-shorelines/14AC6D AB72B95B11A5685958FE907CB3

Nieuwenhout, C., & Andreasson, L. M. (2023). The legal framework for artificial energy islands in the northern seas. The International Journal of Marine and Coastal Law, 39(1), 39-72.

https://doi.org/10.1163/15718085-bja10151

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	73

Zhao, K., Wang, Y., & Liu, P. L. F. (2024). A guide for selecting periodic water wave theories-Le Méhauté (1976)’s graph revisited. Coastal Engineering, 188, 104432. https://doi.org/10.1016/j.coastaleng.2023.104432

Calapini, W. D., Tan, F. J., Monjardin, C. E. F., & Gacu, J. G. (2025). Geospatial Analysis of Flood Hazard Using GIS-Based Hydrologic–Hydraulic Modeling: A Case of the Cagayan River Basin, Philippines. Geomatics, 5(4), 64. https://doi.org/10.3390/geomatics5040064

Tzepkenlis, A., Grammalidis, N., Kontopoulos, C., Charalampopoulou, V., Kitsiou, D., Pataki, Z., ... & Nitis, T. (2022). An integrated monitoring system for coastal and Riparian areas based on remote sensing and machine learning. Journal of Marine Science and Engineering, 10(9), 1322. https://scholar.google.com/scholar?hl=en&as_sdt=0%2C5&q=An+Integrated+Monitoring

+System+for+Coastal+and+Riparian+Areas+Based+on+Remote+Sensing+and+Machine+ Learning&btnG=#d=gs_qabs&t=1783051264543&u=%23p%3D6TQSKAxvEIgJ

Igbokwe, J. I., Obasohan, J. N., & Igbokwe, E. C. (2024). GIS-based analytical hierarchy process modelling and mapping of erosion vulnerability in the coastal areas of Rivers State, Nigeria. Asian Journal of Geographical Research, 7(2), 11-25. https://scholar.google.com/scholar?hl=en&as_sdt=0%2C5&q=GIS-Based+Analytical+Hie rarchy+Process+Modelling+and+Mapping+of+Erosion+Vulnerability+in+the+Coastal+Ar

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	74

eas+of+Rivers+State%2C+Nigeria&btnG=#d=gs_qabs&t=1783052020632&u=%23p%3 D6bOChXY7WQkJ

Cao, C., Zhu, K., Cai, F., Qi, H., Liu, J., Lei, G., ... & Su, Y. (2022). Vulnerability evolution of coastal erosion in the Pearl River Estuary great bay area due to the influence of human activities in the past forty years. Frontiers in Marine Science, 9, 847655. https://scholar.google.com/scholar?hl=en&as_sdt=0%2C5&q=Vulnerability+Evolution+of

+Coastal+Erosion+in+the+Pearl+River+Estuary+Great+Bay+Area+Due+to+the+Influenc e+of+Human+Activities+in+the+Past+Forty+Years&btnG=#d=gs_qabs&t=17830529044 26&u=%23p%3D-eeeAwjkefIJ

Amos, D., & Akib, S. (2023). A review of coastal protection using artificial and natural countermeasures—Mangrove vegetation and polymers. Eng, 4(1), 941-953. https://scholar.google.com/scholar?hl=en&as_sdt=0%2C5&q=A+Review+of+Coastal+Pr otection+Using+Artificial+and+Natural+Countermeasures%E2%80%94Mangrove+Veget ation+and+Polymers&btnG=#d=gs_qabs&t=1783054362672&u=%23p%3DJ8OwdbFVFr IJ

Jordan, P., & Fröhle, P. (2022). Bridging the gap between coastal engineering and nature conservation? A review of coastal ecosystems as nature-based solutions for coastal protection. Journal of Coastal Conservation, 26(2), 4. https://link.springer.com/article/10.1007/s11852-021-00848-x

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	75

Perricone, V., Mutalipassi, M., Mele, A., Buono, M., Vicinanza, D., & Contestabile, P. (2023). Nature-based and bioinspired solutions for coastal protection: an overview among key ecosystems and a promising pathway for new functional and sustainable designs.

ICES Journal of Marine Science, 80(5), 1218-1239. https://academic.oup.com/icesjms/article/80/5/1218/7181089?utm_source=chatgpt.com&l ogin=false

Singhvi, A., Luijendijk, A. P., & van Oudenhoven, A. P. (2022). The grey–green spectrum: A review of coastal protection interventions. Journal of https://www.researchgate.net/publication/359026259_The_grey_-_green_spectrum_A_rev iew_of_coastal_protection_interventions

Taber, K. S. (2018). The use of Cronbach’s alpha when developing and reporting research instruments in science education. Research in science education, 48(6), 1273-1296. https://link.springer.com/article/10.1007/s11165-016-9602-2

Li, C., & Fang, S. (2026). Coastal Land Use Transitions and Their Cascading Impacts on Ecosystem Resilience: A Global Bibliometric Review. Regional Ecology and Management, 1(1), 7.

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	76

https://scholar.googleusercontent.com/scholar?q=cache:4qxTOK8P5esJ:scholar.google.co m/+Coastal+Land+Use+Transitions+and+Their+Cascading+Impacts++on+Ecosystem+Re silience:+A+Global+Bibliometric+Review&hl=en&as_sdt=0,5

Gao, W., Du, J., Gao, S., Xu, Y., Li, B., Wei, X., ... & Li, P. (2023). Shoreline change due to global climate change and human activity at the Shandong Peninsula from 2007 to 2020. Frontiers in Marine Science, 9, 1123067. https://www.frontiersin.org/journals/marine-science/articles/10.3389/fmars.2022.1123067/ full

Tora, D., Fontolan, G., Fracaros, S., & Bezzi, A. (2026). Coastal Vulnerability and Risk Analysis Along the Littoral of Togo. Coasts, 6(2), 18.

https://www.mdpi.com/2673-964X/6/2/18

Elemin, S. A., Fekhaoui, M., Cheikh, M. A. S., Pizzigalli, C., Sidoumou, Z., & Avoulwatt,

M. (2026). Port-induced shoreline change and ecological implications in an arid coastal system: Evidence from N’Diago Port, Mauritania. Ecological Engineering & Environmental Technology, 27(5), 359-375.

https://www.ecoeet.com/Port-induced-shoreline-change-and-ecological-implications-in-an

-arid-coastal-system,220571,0,2.html

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	77

Senatilleke, U., Herath, R., Fonseka, P. U., Kantamaneni, K., & Rathnayake, U. (2026). Assessment of Shoreline Change in Southeast Ireland Using Geospatial Techniques. Sustainability, 18(7), 3280.

https://www.mdpi.com/2071-1050/18/7/3280

Tikekar, O., Saha, S., Deshpande, G., & Sengupta, S. (2026). Integrated DSAS–InVEST modeling for quantitative assessment of shoreline dynamics and coastal exposure along the raigad coast, India. Environmental Systems Research. https://www.researchgate.net/publication/404945223_Integrated_DSAS-InVEST_modelin g_for_quantitative_assessment_of_shoreline_dynamics_and_coastal_exposure_along_the

_raigad_coast_India/citations

U.S Geological Survey. (2023). Coastal Change Hazards Program. https://www.usgs.gov/programs/cmhrp

Luijendijk, A., Hagenaars, G., Ranasinghe, R., Baart, F., Donchyts, G., & Aarninkhof, S. (2018). The state of the world’s beaches. Scientific reports, 8(1), 6641. https://scholar.google.com/scholar?hl=en&as_sdt=0%2C5&q=The+State+of+the+World% 27s+Beaches&btnG=#d=gs_qabs&t=1782985350024&u=%23p%3DCCub87tRruQJ

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	78

Osondu, I., Imoni, O., Chukwuemeka, P., Amos, M. D., Ajibade, D. I., Mene-Ejegi, O. O.,

... & Akajiaku, C. U. (2025). Machine learning-based shoreline change prediction and erosion analysis: a case study of Ogu/Bolo, Nigeria. Discover Civil Engineering, 2(1), 230.

https://scholar.google.com/scholar?hl=en&as_sdt=0%2C5&q=Machine+learning-based+s horeline+change+prediction+and+erosion+analysis%3A+a+case+study+of+Ogu%2FBolo

%2C+Nigeria&btnG=#d=gs_qabs&t=1782987914552&u=%23p%3DR82270NyVHcJ

Thieler, E. R., Himmelstoss, E. A., Zichichi, J. L., & Ergul, A. (2009). The Digital Shoreline Analysis System (DSAS) version 4.0-an ArcGIS extension for calculating shoreline change (No. 2008-1278). US Geological Survey. https://pubs.usgs.gov/publication/ofr20081278

Nerves, A., Rivera, F. D., Blanco, A., Tirol, Y., & Nadaoka, K. (2024). Shoreline Change Analysis in New Washington, Aklan using Digital Shoreline Analysis System (DSAS). ISPRS Annals of the Photogrammetry, Remote Sensing and Spatial Information Sciences, 10, 111-117.

https://isprs-annals.copernicus.org/articles/X-5-2024/111/2024/isprs-annals-X-5-2024-111

-2024.html

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	79

Zhang, Y., Ouyang, Z., Xu, C., Wu, T., & Lu, F. (2024). A multi-hazard framework for coastal vulnerability assessment and climate-change adaptation planning. Environmental and Sustainability Indicators, 21, 100327. https://www.sciencedirect.com/science/article/pii/S2665972723001046

Sauvé, P., Bernatchez, P., & Glaus, M. (2022). Multicriteria decision analysis to assist in the selection of coastal defence measures: Involving coastal managers and professionals in the identification and weighting of criteria. Frontiers in Marine Science, 9, 845348. https://www.frontiersin.org/journals/marine-science/articles/10.3389/fmars.2022.845348/f ull

WILSON, E. T., & Liberia, T. N. A. E. P. A. (2019). COASTAL ZONE’S TECHNOLOGY NEEDS ASSESSMENT FOR CLIMATE CHANGE ADAPTATION.

https://ekmsliberia.info/wp-content/uploads/2020/12/tna-report-coastal-zone-liberia.pdf

Gu, J., Wei, X., Han, Y., Zeng, J., Hu, M., & Gong, Z. (2025). A Conflict-Coordination Framework for Constructing Living Shorelines: A Case Study of Ecological Seawalls. Sustainability, 17(22), 10050.

https://www.mdpi.com/2071-1050/17/22/10050

Narafu, T., Shimizu, T., Sanada, Y., Tamura, Y., Mita, N., Takahashi, S., ... & Itsuki, A. (2015). Lessons learnt from damage to buildings by Bohol earthquake and typhoon

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	80

Yolanda 2013 in the Philippines. Bulletin of International Institute of Seismology and Earthquake Engineering, 49, 39-61. https://scholar.googleusercontent.com/scholar?q=cache:asVO9xfDtbEJ:scholar.google.co m/+LESSONS+LEARNT+FROM+DAMAGE+TO+BUILDINGS++BY+BOHOL+EART HQUAKE+AND+TYPHOON++YOLANDA+2013+IN+THE+PHILIPPINES+&hl=en&

as_sdt=0,5

Bartolome, I. S., & Griño Jr, A. (2026). RELIABILITY ANALYSIS OF DAMPALIT MEGA DIKE USING MONTE CARLO SIMULATION AGAINST SLIDING FAILURE. GEOMATE Journal, 30(137), 43-51.

https://scholar.googleusercontent.com/scholar?q=cache:DBRLdy-hXWAJ:scholar.google. com/+RELIABILITY+ANALYSIS+OF+DAMPALIT+MEGA+DIKE+USING++MONT E+CARLO+SIMULATION+AGAINST+SLIDING+FAILURE&hl=en&as_sdt=0,5

Dodgson, J. S., Spackman, M., Pearman, A., & Phillips, L. D. (2009). Multi-criteria analysis: a manual.

https://scholar.google.com/scholar?hl=en&as_sdt=0%2C5&q=Multi-Criteria+Analysis%3 A+A+Manual.+UK+Department+for+Communities+and+Local+Government.&btnG=#d

=gs_qabs&t=1783059610354&u=%23p%3Djv4K4fj43pwJ

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	81

## APPENDICES

### Appendix A. Work Breakdown Schedule

| No. | Year | 2026 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Month | Jan. | Feb. | March | April | May | June | July | Aug. | Sept. | Oct. |
|  | Research Activities |  |  |  |  |  |  |  |  |  |  |
| 1 | TOPIC SELECTION |  |  |  |  |  |  |  |  |  |  |
| 2 | GAP IDENTIFICATION AND PROPOSED TITLE ORGANIZATION |  |  |  |  |  |  |  |  |  |  |
| 3 | PROBLEM STATEMENT |  |  |  |  |  |  |  |  |  |  |
| 4 | OBJECTIVES |  |  |  |  |  |  |  |  |  |  |
| 5 | CONCEPTUAL FRAMEWORK |  |  |  |  |  |  |  |  |  |  |
| 6 | LITERATURE REVIEW |  |  |  |  |  |  |  |  |  |  |
| 7 | METHODOLOGY DESIGN |  |  |  |  |  |  |  |  |  |  |
| 8 | PROPOSAL DRAFT |  |  |  |  |  |  |  |  |  |  |
| 9 | PROPOSAL SUBMISSION |  |  |  |  |  |  |  |  |  |  |
| 10 | PROPOSAL DEFENSE |  |  |  |  |  |  |  |  |  |  |
| 11 | DATA COLLECTION |  |  |  |  |  |  |  |  |  |  |
| 12 | PILOT TESTING |  |  |  |  |  |  |  |  |  |  |
| 13 | STATISTICAL TOOLS |  |  |  |  |  |  |  |  |  |  |
| 14 | RESULTS & DISCUSSION |  |  |  |  |  |  |  |  |  |  |
| 15 | WRITING REVISION |  |  |  |  |  |  |  |  |  |  |
| 16 | FINAL DEFENSE |  |  |  |  |  |  |  |  |  |  |
| 17 | FORMATTING |  |  |  |  |  |  |  |  |  |  |

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	82

| 18 | FINAL PAPER |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

### Appendix B. Sample Research Questionnaire

Dear Respondent,

We are fourth-year civil engineering students of Cagayan State University-Carig Campus currently conducting a research entitled, “Development of Construction Management Framework for Shoreline Protection Structures Based on Coastal Erosion Risk Levels in Aparri, Cagayan ”.

In line with this, we humbly request your participation in answering our survey questionnaire intended for Civil Engineers, DPWH Engineers, Contractors, Coastal/Environmental Engineers, and LGU Technical Personnel. The questionnaire aims to evaluate different shoreline structures and proposes a framework based on your professional knowledge and experience. It will only take a few minutes to accomplish and maybe answered in your most convenient time. Rest assured that all information gathered will be used only for academic purposes.

We would like to sincerely thank you for your support and cooperation. Additionally, we would be grateful for your willingness to participate in this study, as your insights will significantly contribute to the completion and success of our study.

Your effort in accomplishing this questionnaire is highly appreciated. Thank you very much.

Yours truly,

Rizabell F. Bruno

Sandara Marie M. Cabauatan

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	83

Ross Ann D. Mora Phoebe Kate S. Ubando

# EVALUATION OF SHORELINE PROTECTION STRUCTURES

Name (Optional):

Position:

Office/Agency:

Years of Experience:

Civil Engineer

DPWH Engineer

Coastal/Environmental Engineer

Contractor

LGU Technical Personnel

Less than 5 years

5–10 years

11–20 years

More than 20 years

Have you worked on or supervised a Shoreline Protection Structures?

Yes	 No

Are you familiar with different types of Shoreline Protection Structures (Seawalls, Revetments, Riprap, Breakwater, Mangrove Rehabilitation) ?

Yes	 No

Have you received any education or training related to Coastal Engineering or Shoreline Protection?

Yes	 No

INSTRUCTION: Please check the rate of each shoreline protection structures based on the criteria below using the scale:

5 - Highly Appropriate 4 - Appropriate

3 - Moderately Appropriate

2 - Slightly Appropriate 1 - Not Appropriate

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	84

### Seawalls

| Statements | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 1. Seawalls are structurally stable. |  |  |  |  |  |
| 2. Seawalls provide adequate protection against coastal erosion . |  |  |  |  |  |
| 3. Seawalls provide a cost-effective solution for shoreline protection. |  |  |  |  |  |
| 4. Seawalls are your most recommended erosion protection structure according to its durability. |  |  |  |  |  |
| 5. Seawalls require manageable maintenance throughout their service life. |  |  |  |  |  |
| 6. Environmental benefits of seawalls outweigh its potential adverse environmental impact. |  |  |  |  |  |

### Revetments

| Statements | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 1. Revetments are structurally stable. |  |  |  |  |  |
| 2. Revetments provide adequate protection against coastal erosion . |  |  |  |  |  |
| 3. Revetments provide a cost-effective solution for shoreline protection. |  |  |  |  |  |
| 4. Revetments are your most recommended erosion protection structure according to its durability. |  |  |  |  |  |
| 5. Revetments require manageable maintenance throughout their service life. |  |  |  |  |  |
| 6. Environmental benefits of revetments outweigh its potential adverse environmental impact. |  |  |  |  |  |

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	85

### Riprap

| Statements | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 1. Ripraps are structurally stable. |  |  |  |  |  |
| 2. Ripraps provide adequate protection against coastal erosion . |  |  |  |  |  |
| 3. Ripraps provide a cost-effective solution for shoreline protection. |  |  |  |  |  |
| 4. Ripraps are your most recommended erosion protection structure according to its durability. |  |  |  |  |  |
| 5. Ripraps require manageable maintenance throughout their service life. |  |  |  |  |  |
| 6. Environmental benefits of ripraps outweigh its potential adverse environmental impact. |  |  |  |  |  |

### Breakwater

| Statements | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 1. Breakwaters are structurally stable. |  |  |  |  |  |
| 2. Breakwaters provide adequate protection against coastal erosion . |  |  |  |  |  |
| 3. Breakwater provides a cost-effective solution for shoreline protection. |  |  |  |  |  |
| 4. Breakwater is your most recommended erosion protection structure according to its durability. |  |  |  |  |  |
| 5. Breakwater requires manageable maintenance throughout their service life. |  |  |  |  |  |
| 6. Environmental benefits of breakwater outweigh its potential adverse environmental impact. |  |  |  |  |  |

CAGAYAN STATE UNIVERSITY CARIG CAMPUS

COLLEGE OF ENGINEERING

AND ARCHITECTURE	86

### Mangrove Rehabilitation

| Statements | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 1. Mangrove rehabilitation is structurally stable. |  |  |  |  |  |
| 2. Mangrove rehabilitation provides adequate protection against coastal erosion . |  |  |  |  |  |
| 3. Mangrove rehabilitation provides a cost-effective solution for shoreline protection. |  |  |  |  |  |
| 4. Mangrove rehabilitation is your most recommended erosion protection structure according to its durability. |  |  |  |  |  |
| 5. Mangrove rehabilitation requires manageable maintenance throughout their service life. |  |  |  |  |  |
| 6. Environmental benefits of mangrove rehabilitation outweigh its potential adverse environmental impact. |  |  |  |  |  |